## 1st QTR 2021
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
As of the 1st Quarter of CY 2021
Provincial Government of Benguet
Program or Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions if any | Balance | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
DOH Funds |  | Province of Benguet
1 | Lead Fund |  | 2000000 | 2006-01-29 | 2006-07-01 | 99.77% | 1995401.98 |  | 4598.02 |  | On Going
2 | Maternal, Newborn & Child Health & Nutrition |  | 1892235.43 | 1905-06-27 | 1905-07-01 | 96.05% | 1817520.4 |  | 74715.03 | 1 | Project Implementation extended
3 | 2013, 2015,2016 & 2017 Fixed & Variable Tranche |  | 4650000 | 2018-08-17 | 2020-12-31 | 99.96% | 4647979.86 |  | 2020.14 | 2 | Project Implementation extended
4 | Medical Assistance to Indigent Patients of BeGH |  | 11000003 | 2021-03-23 | 2021-12-31 | 0% | 0 |  | 11000003 |  | On Going
5 | Medical Assistance to Indigent Patients of District Hospitals |  | 6090000 | 2020-01-01 |  | 29.41% | 1790864.99 |  | 4299135.01 |  | On Going
Atok District Hospital
Northern Benguet District Hospital
Dennis Molintas District Hospital
Itogon District Hospital
Kapangan District Hospital
6 | National Nutrition Council (Crown Award) |  | 500000 | 2016-12-13 |  | 21.35% | 106750 |  | 393250 |  | On Going
7 | Repair of KDH and BeGH |  | 10140726 | 2019-01-04 |  | 50.86% | 5157590.32 |  | 4983135.68 |  | On Going
8 | Repair of ADH |  | 3500000 | 2021-01-08 |  | 0% | 0 |  | 3500000
9 | Construction of Temporary Treatment and Monitoring Facility |  | 10000000 | 2021-01-08 |  | 0% | 0 |  | 10000000
10 | Grant of AHDP and CoVID-19 SRA |  | 12432999.47 | 2021-01-08 | 2021-03-31 | 78.74% | 9789707.04 |  | 2643292.43
11 | Provision of Life Insurance, Accomodation, Transportation and Meals |  | 2513830.31 | 2021-03-23 | 2021-03-31 | 3.74% | 94125 |  | 2419705.31
DA Funds |  | Province of Benguet
1 | NAFC |  | 219678.79 | 2020-01-01 |  | 69.36% | 152370 |  | 67308.79 |  | Continuing Project
2 | Purchase of Vehicles for BAPTC |  | 10620000 | 2017-06-01 |  | 83.45% | 8862288 |  | 1757712 | 1 | Project Implementation extended
3 | Prize of the Province as Regional winner of the NOAAA |  | 1000000 | Various dates |  | 86.14% | 861398.59 |  | 138601.41 |  | On Going
DA Funds
4 | PRDP - IBUILD
| LGU Counterpart |  | 77272292.23 | 2021-01-01 |  | 30.35% | 23450340.01 |  | 53821952.22 |  | On going
| LP |  | 187602721.23 | 2021-01-01 |  | 100% | 187602720.19 |  | 1.04 |  | On going
| GOP |  | 23450340.19 | 2021-01-01 |  | 100% | 23450340.02 |  | 0.17 |  | On going
5 | PRDP - IREAP
| LGU Counterpart |  | 3705555.2 | 2021-01-01 |  | 70.77% | 2622566.2 |  | 1082989 |  | On going
| LP |  | 9846882.6 | 2021-01-01 |  | 77.16% | 7597698.6 |  | 2249184 |  | On going
| GOP |  | 3282294.2 | 2021-01-01 |  | 77.16% | 2532566.2 |  | 749728 |  | On going
DBM Funds |  | Province of Benguet
1 | Fund to cover funding requirment to aid in the recovery and reconstruction of the economy and livelihood in the LGUs that are directly affected by Taal Volcano eruption, Typhoon Quinta, Rolly and Ulysses |  | 20070985 | 2021-02-26 | 2022-12-31 |  | 0 |  | 20070985
2 | Fund to cover funding requirements for the Financial Assistance to LGUs affected by Typhoon Ulysses |  | 3451904 | 2020-12-31 | 2021-12-31 |  | 0 |  | 3451904
3 | Improvement of Besocol - Ballay FMR located at Ballay, Kabayan |  | 20000000 | 2020-10-27 | 2021-12-31 |  | 0 |  | 20000000 |  | On-going
4 | Rehab/Relocation of landslide victims of Loacan Anteg-in, Itogon |  | 3000000 | 2009-06-01 |  | 30.4% | 912148.4 |  | 2087851.6 |  | Requested for realignment to augment funds for COVID 19 expenses
DOLE Funds |  | Province of Benguet
1 | Provinsion of Agricultural Machineries for Lusod ARC-MPC |  | 397035.68 | 2020-12-14 | 2021-12-31 |  | 0 |  | 397035.68 |  | Procurement Ongoing
DILG Funds |  | Province of Benguet | [6 empty] | 0
1 | Provincial Road Network Development Plan (PRNDP) Kalsada Program (inclusive of provincial counterpart) |  | 110229060.11 | Feb 2016 |  | 96.03% | 105850130.32 |  | 4378929.79 |  | On Going
2 | Conditional Matching Grant to Provinces (CMGP) 2017 | Province of Benguet | 133244985 | Aug 2017 |  | 100% | 133244985 |  | 0 |  | Fully Liquidated
3 | Conditional Matching Grant to Provinces (CMGP) 2018 |  | 63829590 | May 2018 |  | 100% | 63829590 |  | 0 |  | Fully Liquidated
4 | Conditional Matching Grant to Provinces (CMGP) 2019 |  | 86127223 | Nov 2019 |  | 19.06% | 16412176.8 |  | 69715046.2 |  | On Going
5 | Conditional Matching Grant to Provinces (CMGP) 2020 |  | 78199298 | Oct 2020 |  | 8.46% | 6615000.1 |  | 71584297.9 |  | On Going
Office of the President - LGSF - Financial Assistance for use at Benguet General Hospital |  | Province of Benguet | 3000000 | 2020-11-24 |  | 45.41% | 1362429.54 |  | 1637570.46
Revolving Fund for Drugs and Medicines of Various District Hospitals under the Pooled Procurement System |  | Province of Benguet | 15052018.85 | 2009-10-01 |  |  | 1766918.84 |  | 13285100.01 |  | Revolving Fund
Housing Lot - Wangal |  | Province of Benguet | 4078809.58 | Various dates |  | 67.42% | 2750093.52 |  | 1328716.06 |  | Continuing Fund/Project
Provincial Counterpart for the Construction of Benguet Coffee Trading Center |  | Province of Benguet | 4000000 | 2016-01-01 |  | 59.41% | 2376515.96 |  | 1623484.04 |  | On Going
Provincial Counterpart to CHARMP II Sub-Projects |  | Province of Benguet | 69329114.1 | Various dates |  | 64.37% | 44624611.55 |  | 24704502.55 |  | On Going
Provincial Counterpart to Special Projects |  | Province of Benguet | 147582919 | Various dates |  | 57% | 84128523.59 |  | 63454395.41 |  | On Going | 2018 | 2019
Provincial Study Now Pay Later Program Fund |  | Province of Benguet | 20000000 | Various dates |  |  | 0 |  | 20000000 |  | Revolving Fund
Donation from Philex Mines for Typhoon Victims of Benguet |  | Province of Benguet | 500000 | 2011-04-29 |  | 94.46% | 472300 |  | 27700 |  | Realigned to augment funds for COVID 19 expenses
Donation from Reed Elsevier Philippines Lex Machina Team |  | Province of Benguet | 50348.2 | 2019-12-12 |  | 44.89% | 22600 |  | 27748.2 |  | On-going
Donation from Atty Gerard Felipe - Prizes for the Benguet Youth Competition |  | Province of Benguet | 68000 | 2020-12-21 |  | 100% | 68000 |  | 0
Adivay fund |  | Province of Benguet | 2074594.63 | Various dates |  | 73.58% | 1526458.67 |  | 548135.96 |  | Continuing Fund/Project |  | Balance
Financial Benefits from GenCo's - ER 1-94 (DLF & RWMHEEF) | [12 empty] | DLF | RWMHEEF
1 | San Roque Power Corporation | Province of Benguet | 0 | Various dates |  | #DIV/0! | -15639162.89 |  | 15639162.89 |  | On Going |  | DLF | RWMHEEF
2 | HEDCOR, Inc |  | 0 | Various dates |  | #DIV/0! | -7215273.81 |  | 7215273.81 |  | On Going
3 | Luzon Hydro Corporation |  | 0 | Various dates |  | #DIV/0! | -4561770.97 |  | 4561770.97 |  | On Going | 0 | 5574578.96 | 10064583.93 | 15639162.89
4 | SN Aboitiz - Benguet |  | 0 | Various dates |  | #DIV/0! | -11962163.17 |  | 11962163.17 |  | On Going | 0 | 4501156.15 | 7461007.02 | 11962163.17
5 | SNAPBI - BHEPP |  | 0 | Various dates |  | #DIV/0! | -2306646.71 |  | 2306646.71 |  | On Going | 0 | 715112.99 | 1591533.72 | 2306646.71
SN - ABOITIZ CSR |  | Province of Benguet | [6 empty] | 0 |  |  | 0 | 1775935.04 | 5439338.77 | 7215273.81
1 | Various Infrastructure Projects |  | 4712606.33 | 2020-01-01 |  | 20.46% | 964097.44 |  | 3748508.89 |  | On Going | 0 | 1362785.96 | 3198985.01 | 4561770.97
2 | Assistance in ensuring Good Governance in the Province of Benguet thru Strategic Management Enhancement |  | 1562044.44 | 2019-01-29 |  | 61.51% | 960853.56 |  | 601190.88 |  | On Going | 0 |  |  | 41685017.55
3 | Developing the Benguet Agri Eco Farm as an Agri-Innovation Center and Living Museum |  | 2379964 | 2019-12-19 |  | 90.19% | 2146441.64 |  | 233522.36 |  | On Going | 42146853.92 |  |  | 41677883.8
Interlocal Health Zone Fund |  | Province of Benguet | [6 empty] | 0
1 | Mt. Trail ILHZ |  | 1474402.66 | 2020 |  | 40% | 589820 |  | 884582.66 |  | Continuing Fund/Project
2 | BLISTT BeGH |  | 339028.92 | 2020 |  | 5.52% | 18720 |  | 320308.92 |  | Continuing Fund/Project
Disaster Risk Reduction and Management (DRRM) Fund: |  | Province of Benguet
| CY 2015 |  | 17791448.53 | 2015-12-31 |  | 88.8% | 15798448.53 |  | 1993000 |  | On going
| CY 2016 |  | 13252198.94 | 2016-12-31 |  | 97.19% | 12880426.58 |  | 371772.36 |  | On going
| CY 2017 |  | 26535352.04 | 2017-12-31 |  | 71.63% | 19006556.06 |  | 7528795.98 |  | On going
| CY 2018 |  | 33698839.16 | 2018-12-31 |  | 77.14% | 25995710.61 |  | 7703128.55 |  | On going
| CY 2019 |  | 30047050.28 | 2019-12-31 |  | 10.94% | 3287679.31 |  | 26759370.97 |  | On-going
| CY 2020 |  | 15034790.76 | 2020-12-31 |  | 0% | 0 |  | 15034790.76
| Cash Donations from various donors |  | 7749376.83 | 2020 |  | 48.15% | 3731338.75 |  | 4018038.08 |  | On-going
|  |  | 1320582546.69 |  |  |  | 792189784.62 | 0 | 528392762.07
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Note on D58: user: 2015 - 40,000,000 2017 - 36,374,669 2018 - 19,815,000 2019 - 29,789,000 2020 - 21,604,250