## Sheet1
Project | Phase |  | From Date | To Date | Project | Phase | Schedule Performance | Cost Performance
Project 1 | Design | Plan | 2023-01-12 | 2023-01-18 | Project 1 | Design | On Time | At Cost
|  | Actual | 2023-01-12 | 2023-01-18 |  | Coding | Overrun | Overrun
[5 empty] | Project2 | Requirements | Overrun | Underrun
| Coding | Plan | 2023-01-19 | 2023-03-12 |  | Design | Underrun | Overrun
|  | Actual | 2023-01-16 | 2023-03-28 |  | Testing | On Time | At Cost
Project2 | Requirements | Plan | 2024-08-01 | 2024-08-12
|  | Actual | 2024-08-10 | 2024-08-18
| Design | Plan | 2024-08-14 | 2024-08-31
|  | Actual | 2024-08-10 | 2024-08-29
| Testing | Plan | 2024-09-01 | 2024-09-10
|  | Actual | 2024-08-31 | 2024-09-10
RESULT
PROBLEM
Convert the problem table into result table.
Schedule Performance
On Time: Actual To Date = Plan To Date
Overrun: Actual To Date > Plan To Date
Underrun: Actual To Date < Plan To Date
Cost Peformance:
At Cost: Actual Networkdays = Plan Networkdays
Overrun: Actual Networkdays > Plan Networkdays
Underrun: Actual Networkdays < Plan Networkdays