## Data
Project_ID | Start_Date | End_Date | Market | Job_Type | PM | Contract_Revenue | Budget_Cost_BAC | Cost_To_Date_AC | Projected_Final_Cost_EAC | Status | Projected_Overrun
PRJ-202501-0001 | 2025-01-02 | 2025-02-13 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 27763.7 | 19174.32 | 17219.75 | 17219.75 | Closed | -1954.57
PRJ-202501-0002 | 2025-01-13 | 2025-02-04 | Light Commercial | Commercial Service | Brandon Shaw | 22738.42 | 16926.07 | 15891.12 | 15891.12 | Closed | -1034.95
PRJ-202501-0003 | 2025-01-25 | 2025-01-28 | Residential | Install - Replacement | Anthony Ruiz | 8333.03 | 5008.08 | 4954.91 | 4954.91 | Closed | -53.17
PRJ-202501-0004 | 2025-01-20 | 2025-01-22 | Residential | Install - Replacement | Luis Martinez | 7265.91 | 4946.88 | 5418.52 | 5418.52 | Closed | 471.64
PRJ-202501-0005 | 2025-01-22 | 2025-01-25 | Residential | Install - New Construction | Anthony Ruiz | 8357.15 | 5257.95 | 4469.26 | 4469.26 | Closed | -788.69
PRJ-202501-0006 | 2025-01-17 | 2025-01-21 | Residential | Service - Major Repair | Derek Collins | 4697.46 | 2826.12 | 2452.81 | 2452.81 | Closed | -373.31
PRJ-202501-0007 | 2025-01-13 | 2025-01-15 | Residential | Install - Replacement | Anthony Ruiz | 4763.13 | 2992.92 | 3268.2 | 3268.2 | Closed | 275.28
PRJ-202501-0008 | 2025-01-02 | 2025-01-06 | Residential | Service - Major Repair | Brandon Shaw | 6113.13 | 4095.47 | 3499.61 | 3499.61 | Closed | -595.86
PRJ-202501-0009 | 2025-01-21 | 2025-01-24 | Residential | Install - Replacement | Brandon Shaw | 7169.92 | 4620.7 | 4061.85 | 4061.85 | Closed | -558.85
PRJ-202501-0010 | 2025-01-24 | 2025-01-27 | Residential | Install - Replacement | Brandon Shaw | 6946.07 | 4542.2 | 4787.33 | 4787.33 | Closed | 245.13
PRJ-202501-0011 | 2025-01-22 | 2025-01-24 | Residential | Install - Replacement | Luis Martinez | 5937.21 | 4125.32 | 5292.83 | 5292.83 | Closed | 1167.51
PRJ-202501-0012 | 2025-01-12 | 2025-01-16 | Residential | Service - Major Repair | Luis Martinez | 5814.42 | 3447.34 | 3831.31 | 3831.31 | Closed | 383.97
PRJ-202501-0013 | 2025-01-09 | 2025-01-13 | Residential | Install - New Construction | Carlos Vega | 7117.81 | 4551.33 | 5166.17 | 5166.17 | Closed | 614.84
PRJ-202501-0014 | 2025-01-13 | 2025-03-10 | Light Commercial | Commercial RTU Replacement | Derek Collins | 27182.58 | 18770.39 | 18058.02 | 18058.02 | Closed | -712.37
PRJ-202501-0015 | 2025-01-18 | 2025-01-20 | Residential | Install - Replacement | Carlos Vega | 6638.21 | 4445.42 | 4931.88 | 4931.88 | Closed | 486.46
PRJ-202501-0016 | 2025-01-09 | 2025-01-12 | Residential | Install - Replacement | Brandon Shaw | 5938.55 | 3902.5 | 3605.4 | 3605.4 | Closed | -297.1
PRJ-202501-0017 | 2025-01-13 | 2025-01-15 | Residential | Service - Major Repair | Luis Martinez | 4734.55 | 2952.32 | 2509.47 | 2509.47 | Closed | -442.85
PRJ-202501-0018 | 2025-01-09 | 2025-02-05 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 24014.67 | 17629.98 | 18127.99 | 18127.99 | Closed | 498.01
PRJ-202501-0019 | 2025-01-25 | 2025-03-03 | Light Commercial | Commercial Service | Derek Collins | 32470.48 | 22586.04 | 21450.25 | 21450.25 | Closed | -1135.79
PRJ-202501-0020 | 2025-01-10 | 2025-01-11 | Residential | Install - Replacement | Carlos Vega | 7751.25 | 5714.86 | 6287.35 | 6287.35 | Closed | 572.49
PRJ-202501-0021 | 2025-01-16 | 2025-01-19 | Residential | Service - Major Repair | Luis Martinez | 5684.11 | 3552.32 | 3245.89 | 3245.89 | Closed | -306.43
PRJ-202501-0022 | 2025-01-11 | 2025-02-08 | Light Commercial | Commercial RTU Replacement | Derek Collins | 30696.44 | 19467.73 | 17594.65 | 17594.65 | Closed | -1873.08
PRJ-202501-0023 | 2025-01-18 | 2025-01-22 | Residential | Install - Replacement | Brandon Shaw | 4478.16 | 3031.72 | 3365.94 | 3365.94 | Closed | 334.22
PRJ-202501-0024 | 2025-01-23 | 2025-01-26 | Residential | Install - Replacement | Brandon Shaw | 7349.62 | 4484.06 | 4060.86 | 4060.86 | Closed | -423.2
PRJ-202502-0025 | 2025-02-04 | 2025-02-28 | Light Commercial | Commercial Service | Derek Collins | 13256.31 | 7851.43 | 7976.71 | 7976.71 | Closed | 125.28
PRJ-202502-0026 | 2025-02-04 | 2025-02-07 | Residential | Service - Major Repair | Derek Collins | 6852.37 | 4809.37 | 5149.48 | 5149.48 | Closed | 340.11
PRJ-202502-0027 | 2025-02-13 | 2025-02-17 | Residential | Install - Replacement | Carlos Vega | 3943.35 | 2452.62 | 2564.94 | 2564.94 | Closed | 112.32
PRJ-202502-0028 | 2025-02-21 | 2025-02-24 | Residential | Install - Replacement | Carlos Vega | 7983.58 | 5658.5 | 6106.02 | 6106.02 | Closed | 447.52
PRJ-202502-0029 | 2025-02-14 | 2025-02-16 | Residential | Service - Major Repair | Anthony Ruiz | 5957.73 | 3183.49 | 4021.65 | 4021.65 | Closed | 838.16
PRJ-202502-0030 | 2025-02-01 | 2025-02-03 | Residential | Install - New Construction | Carlos Vega | 8060.09 | 5764.16 | 5033.53 | 5033.53 | Closed | -730.63
PRJ-202502-0031 | 2025-02-17 | 2025-02-20 | Residential | Service - Major Repair | Derek Collins | 3944.72 | 2132.89 | 2008.32 | 2008.32 | Closed | -124.57
PRJ-202502-0032 | 2025-02-05 | 2025-02-09 | Residential | Install - Replacement | Anthony Ruiz | 5854.97 | 4110.86 | 4450.79 | 4450.79 | Closed | 339.93
PRJ-202502-0033 | 2025-02-10 | 2025-02-12 | Residential | Install - New Construction | Brandon Shaw | 8058.1 | 5188.75 | 4549.48 | 4549.48 | Closed | -639.27
PRJ-202502-0034 | 2025-02-11 | 2025-02-13 | Residential | Service - Major Repair | Anthony Ruiz | 5248.61 | 3159.82 | 3766.46 | 3766.46 | Closed | 606.64
PRJ-202502-0035 | 2025-02-16 | 2025-03-08 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 39786.56 | 24400.71 | 28399.8 | 28399.8 | Closed | 3999.09
PRJ-202502-0036 | 2025-02-14 | 2025-02-18 | Residential | Install - Replacement | Brandon Shaw | 6236.4 | 4365.34 | 3492.28 | 3492.28 | Closed | -873.06
PRJ-202502-0037 | 2025-02-18 | 2025-02-22 | Residential | Install - Replacement | Derek Collins | 6525.67 | 4000.96 | 3768.01 | 3768.01 | Closed | -232.95
PRJ-202502-0038 | 2025-02-24 | 2025-04-19 | Light Commercial | Tenant Improvement | Anthony Ruiz | 28008.95 | 20111.12 | 21609.17 | 21609.17 | Closed | 1498.05
PRJ-202502-0039 | 2025-02-22 | 2025-02-26 | Residential | Service - Major Repair | Derek Collins | 5814.84 | 3653.9 | 3930.54 | 3930.54 | Closed | 276.64
PRJ-202502-0040 | 2025-02-22 | 2025-02-23 | Residential | Install - Replacement | Brandon Shaw | 6619.64 | 3411.22 | 3532.93 | 3532.93 | Closed | 121.71
PRJ-202502-0041 | 2025-02-06 | 2025-02-10 | Residential | Install - Replacement | Carlos Vega | 7888.16 | 4976.96 | 5335.5 | 5335.5 | Closed | 358.54
PRJ-202502-0042 | 2025-02-07 | 2025-02-27 | Light Commercial | Tenant Improvement | Anthony Ruiz | 32154.01 | 21437.46 | 22726.09 | 22726.09 | Closed | 1288.63
PRJ-202502-0043 | 2025-02-01 | 2025-02-03 | Residential | Service - Major Repair | Luis Martinez | 6815.54 | 4720.49 | 4584.48 | 4584.48 | Closed | -136.01
PRJ-202503-0044 | 2025-03-25 | 2025-05-14 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 44245.19 | 32609.63 | 34123.53 | 34123.53 | Closed | 1513.9
PRJ-202503-0045 | 2025-03-09 | 2025-03-11 | Residential | Install - Replacement | Derek Collins | 7492.24 | 4661.61 | 4800.76 | 4800.76 | Closed | 139.15
PRJ-202503-0046 | 2025-03-11 | 2025-04-16 | Light Commercial | Tenant Improvement | Anthony Ruiz | 30837.02 | 16960.36 | 18276.65 | 18276.65 | Closed | 1316.29
PRJ-202503-0047 | 2025-03-18 | 2025-03-20 | Residential | Install - Replacement | Carlos Vega | 6166.81 | 4541.32 | 4963.72 | 4963.72 | Closed | 422.4
PRJ-202503-0048 | 2025-03-13 | 2025-03-14 | Residential | Service - Major Repair | Brandon Shaw | 6468.16 | 4354.72 | 4221.79 | 4221.79 | Closed | -132.93
PRJ-202503-0049 | 2025-03-10 | 2025-04-02 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 40799.41 | 25262.1 | 27190.25 | 27190.25 | Closed | 1928.15
PRJ-202503-0050 | 2025-03-10 | 2025-03-13 | Residential | Install - Replacement | Carlos Vega | 6951.2 | 4726.18 | 5018.85 | 5018.85 | Closed | 292.67
PRJ-202503-0051 | 2025-03-23 | 2025-03-25 | Residential | Install - Replacement | Derek Collins | 5889.51 | 3518.84 | 3060.08 | 3060.08 | Closed | -458.76
PRJ-202503-0052 | 2025-03-11 | 2025-03-13 | Residential | Install - Replacement | Derek Collins | 9822.57 | 6286.68 | 5868.51 | 5868.51 | Closed | -418.17
PRJ-202503-0053 | 2025-03-22 | 2025-05-08 | Light Commercial | Commercial RTU Replacement | Derek Collins | 31281.28 | 21947.58 | 23339.84 | 23339.84 | Closed | 1392.26
PRJ-202503-0054 | 2025-03-09 | 2025-03-13 | Residential | Install - New Construction | Brandon Shaw | 7251.19 | 4684.27 | 4907.95 | 4907.95 | Closed | 223.68
PRJ-202503-0055 | 2025-03-11 | 2025-03-13 | Residential | Install - Replacement | Brandon Shaw | 4683.51 | 3080.7 | 3103.93 | 3103.93 | Closed | 23.23
PRJ-202503-0056 | 2025-03-21 | 2025-03-22 | Residential | Install - New Construction | Brandon Shaw | 7513.2 | 4861.38 | 4039.91 | 4039.91 | Closed | -821.47
PRJ-202503-0057 | 2025-03-24 | 2025-05-20 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 14290.86 | 9192.97 | 11208.73 | 11208.73 | Closed | 2015.76
PRJ-202503-0058 | 2025-03-10 | 2025-03-13 | Residential | Service - Major Repair | Brandon Shaw | 6349.54 | 4108.03 | 3973.4 | 3973.4 | Closed | -134.63
PRJ-202503-0059 | 2025-03-03 | 2025-03-06 | Residential | Service - Major Repair | Brandon Shaw | 3821.26 | 2432.58 | 2277.42 | 2277.42 | Closed | -155.16
PRJ-202503-0060 | 2025-03-01 | 2025-03-03 | Residential | Install - Replacement | Carlos Vega | 8319.27 | 5269.78 | 5013.8 | 5013.8 | Closed | -255.98
PRJ-202503-0061 | 2025-03-14 | 2025-03-18 | Residential | Install - Replacement | Anthony Ruiz | 6933.99 | 4281.23 | 4094.45 | 4094.45 | Closed | -186.78
PRJ-202503-0062 | 2025-03-08 | 2025-03-11 | Residential | Service - Major Repair | Anthony Ruiz | 6098.49 | 4453.58 | 3888.81 | 3888.81 | Closed | -564.77
PRJ-202503-0063 | 2025-03-14 | 2025-03-18 | Residential | Install - Replacement | Carlos Vega | 6550.84 | 4317.21 | 4340.34 | 4340.34 | Closed | 23.13
PRJ-202503-0064 | 2025-03-03 | 2025-03-06 | Residential | Install - Replacement | Derek Collins | 4397.04 | 2949.68 | 2500.77 | 2500.77 | Closed | -448.91
PRJ-202503-0065 | 2025-03-20 | 2025-04-11 | Light Commercial | Commercial RTU Replacement | Derek Collins | 33513.55 | 26090.85 | 24791.35 | 24791.35 | Closed | -1299.5
PRJ-202503-0066 | 2025-03-21 | 2025-03-25 | Residential | Service - Major Repair | Carlos Vega | 6292.79 | 3633.52 | 3905.74 | 3905.74 | Closed | 272.22
PRJ-202503-0067 | 2025-03-17 | 2025-03-20 | Residential | Install - Replacement | Brandon Shaw | 5991.29 | 3997.44 | 3917.17 | 3917.17 | Closed | -80.27
PRJ-202503-0068 | 2025-03-22 | 2025-05-19 | Light Commercial | Tenant Improvement | Brandon Shaw | 38672.1 | 26741.57 | 26532.39 | 26532.39 | Closed | -209.18
PRJ-202503-0069 | 2025-03-12 | 2025-05-04 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 36651.5 | 27341.23 | 25892.57 | 25892.57 | Closed | -1448.66
PRJ-202503-0070 | 2025-03-19 | 2025-05-13 | Light Commercial | Tenant Improvement | Carlos Vega | 51114.04 | 35628.91 | 34495.59 | 34495.59 | Closed | -1133.32
PRJ-202503-0071 | 2025-03-24 | 2025-03-26 | Residential | Install - Replacement | Brandon Shaw | 7907.36 | 4735.16 | 4768.38 | 4768.38 | Closed | 33.22
PRJ-202504-0072 | 2025-04-14 | 2025-06-04 | Light Commercial | Tenant Improvement | Carlos Vega | 45998.4 | 27747.83 | 26670.37 | 26670.37 | Closed | -1077.46
PRJ-202504-0073 | 2025-04-09 | 2025-06-01 | Light Commercial | Commercial Service | Anthony Ruiz | 45796.87 | 33606.36 | 28565.41 | 28565.41 | Closed | -5040.95
PRJ-202504-0074 | 2025-04-25 | 2025-04-28 | Residential | Install - Replacement | Brandon Shaw | 5837.33 | 3590.69 | 3272.98 | 3272.98 | Closed | -317.71
PRJ-202504-0075 | 2025-04-22 | 2025-04-25 | Residential | Service - Major Repair | Derek Collins | 5718.58 | 3446.18 | 3433.3 | 3433.3 | Closed | -12.88
PRJ-202504-0076 | 2025-04-08 | 2025-04-12 | Residential | Install - Replacement | Brandon Shaw | 6712.17 | 4463.59 | 4144.27 | 4144.27 | Closed | -319.32
PRJ-202504-0077 | 2025-04-14 | 2025-04-16 | Residential | Install - New Construction | Carlos Vega | 4679.18 | 2724.73 | 2765.59 | 2765.59 | Closed | 40.86
PRJ-202504-0078 | 2025-04-10 | 2025-04-11 | Residential | Install - New Construction | Derek Collins | 7981.37 | 4982.19 | 4720.71 | 4720.71 | Closed | -261.48
PRJ-202504-0079 | 2025-04-08 | 2025-04-09 | Residential | Service - Major Repair | Brandon Shaw | 5966.87 | 3766.41 | 3910.67 | 3910.67 | Closed | 144.26
PRJ-202504-0080 | 2025-04-12 | 2025-04-13 | Residential | Service - Major Repair | Anthony Ruiz | 9122.5 | 6473.29 | 6310.14 | 6310.14 | Closed | -163.15
PRJ-202504-0081 | 2025-04-02 | 2025-04-25 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 36417.25 | 23869.75 | 23819.17 | 23819.17 | Closed | -50.58
PRJ-202504-0082 | 2025-04-01 | 2025-04-15 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 28261.45 | 17761.29 | 18221.58 | 18221.58 | Closed | 460.29
PRJ-202504-0083 | 2025-04-14 | 2025-04-16 | Residential | Service - Major Repair | Anthony Ruiz | 7327.06 | 4678.35 | 4001.93 | 4001.93 | Closed | -676.42
PRJ-202504-0084 | 2025-04-22 | 2025-04-24 | Residential | Install - Replacement | Carlos Vega | 6262.16 | 3902.23 | 3736.58 | 3736.58 | Closed | -165.65
PRJ-202504-0085 | 2025-04-05 | 2025-05-16 | Light Commercial | Tenant Improvement | Brandon Shaw | 52074.01 | 36324.18 | 33842.11 | 33842.11 | Closed | -2482.07
PRJ-202504-0086 | 2025-04-02 | 2025-04-30 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 56609.15 | 37031.39 | 39809.28 | 39809.28 | Closed | 2777.89
PRJ-202504-0087 | 2025-04-17 | 2025-04-21 | Residential | Install - Replacement | Luis Martinez | 4968.44 | 2927.02 | 3286.8 | 3286.8 | Closed | 359.78
PRJ-202504-0088 | 2025-04-16 | 2025-05-26 | Light Commercial | Commercial Service | Derek Collins | 13256.31 | 7986.73 | 8405.07 | 8405.07 | Closed | 418.34
PRJ-202504-0089 | 2025-04-17 | 2025-04-20 | Residential | Install - New Construction | Anthony Ruiz | 5907.46 | 3346.03 | 3864.83 | 3864.83 | Closed | 518.8
PRJ-202504-0090 | 2025-04-15 | 2025-04-16 | Residential | Install - Replacement | Brandon Shaw | 7903.88 | 4311.23 | 4593.48 | 4593.48 | Closed | 282.25
PRJ-202504-0091 | 2025-04-08 | 2025-04-12 | Residential | Install - New Construction | Luis Martinez | 6288.03 | 4066.94 | 4972.67 | 4972.67 | Closed | 905.73
PRJ-202504-0092 | 2025-04-12 | 2025-04-13 | Residential | Install - Replacement | Luis Martinez | 6495.94 | 4610.41 | 4444.66 | 4444.66 | Closed | -165.75
PRJ-202504-0093 | 2025-04-22 | 2025-04-23 | Residential | Install - Replacement | Luis Martinez | 8118.65 | 5497.85 | 6274.3 | 6274.3 | Closed | 776.45
PRJ-202504-0094 | 2025-04-01 | 2025-05-16 | Light Commercial | Commercial RTU Replacement | Derek Collins | 19246.13 | 11957.22 | 11608.5 | 11608.5 | Closed | -348.72
PRJ-202504-0095 | 2025-04-01 | 2025-04-17 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 46783.28 | 31965.18 | 29732.22 | 29732.22 | Closed | -2232.96
PRJ-202504-0096 | 2025-04-05 | 2025-06-03 | Light Commercial | Tenant Improvement | Brandon Shaw | 24990.9 | 18127.08 | 17957.94 | 17957.94 | Closed | -169.14
PRJ-202504-0097 | 2025-04-11 | 2025-04-13 | Residential | Install - New Construction | Luis Martinez | 6454.37 | 3986.15 | 3772.19 | 3772.19 | Closed | -213.96
PRJ-202504-0098 | 2025-04-22 | 2025-04-24 | Residential | Install - New Construction | Anthony Ruiz | 7282.51 | 4668.23 | 5541.96 | 5541.96 | Closed | 873.73
PRJ-202505-0099 | 2025-05-02 | 2025-05-05 | Residential | Service - Major Repair | Luis Martinez | 6534.5 | 4314.66 | 5360.58 | 5360.58 | Closed | 1045.92
PRJ-202505-0100 | 2025-05-11 | 2025-05-12 | Residential | Install - Replacement | Brandon Shaw | 5240.17 | 3207.18 | 3347.02 | 3347.02 | Closed | 139.84
PRJ-202505-0101 | 2025-05-13 | 2025-05-16 | Residential | Install - Replacement | Derek Collins | 7101.82 | 4739.63 | 4080.32 | 4080.32 | Closed | -659.31
PRJ-202505-0102 | 2025-05-15 | 2025-05-18 | Residential | Install - New Construction | Carlos Vega | 8938.52 | 5312.69 | 4547.56 | 4547.56 | Closed | -765.13
PRJ-202505-0103 | 2025-05-22 | 2025-05-26 | Residential | Install - Replacement | Luis Martinez | 5109.91 | 2936.05 | 3380.84 | 3380.84 | Closed | 444.79
PRJ-202505-0104 | 2025-05-09 | 2025-05-11 | Residential | Service - Major Repair | Derek Collins | 9198.59 | 5981.93 | 5962.84 | 5962.84 | Closed | -19.09
PRJ-202505-0105 | 2025-05-21 | 2025-05-22 | Residential | Install - Replacement | Derek Collins | 4759.86 | 3587.56 | 3595.8 | 3595.8 | Closed | 8.24
PRJ-202505-0106 | 2025-05-08 | 2025-06-16 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 27068.94 | 17758.29 | 19384.17 | 19384.17 | Closed | 1625.88
PRJ-202505-0107 | 2025-05-09 | 2025-05-10 | Residential | Service - Major Repair | Brandon Shaw | 6819.28 | 3861.21 | 3678.54 | 3678.54 | Closed | -182.67
PRJ-202505-0108 | 2025-05-03 | 2025-05-07 | Residential | Install - Replacement | Carlos Vega | 8157.62 | 4882.63 | 4503.86 | 4503.86 | Closed | -378.77
PRJ-202505-0109 | 2025-05-23 | 2025-05-25 | Residential | Install - Replacement | Brandon Shaw | 4606.77 | 2762.88 | 2772.47 | 2772.47 | Closed | 9.59
PRJ-202505-0110 | 2025-05-22 | 2025-05-26 | Residential | Service - Major Repair | Derek Collins | 5667.09 | 3516.13 | 3710.95 | 3710.95 | Closed | 194.82
PRJ-202505-0111 | 2025-05-16 | 2025-05-19 | Residential | Service - Major Repair | Brandon Shaw | 7950.35 | 4516.16 | 4131.87 | 4131.87 | Closed | -384.29
PRJ-202505-0112 | 2025-05-12 | 2025-05-13 | Residential | Install - Replacement | Derek Collins | 5538.2 | 3463.3 | 3707.52 | 3707.52 | Closed | 244.22
PRJ-202505-0113 | 2025-05-11 | 2025-05-12 | Residential | Install - Replacement | Brandon Shaw | 6298.06 | 3608.61 | 3045.52 | 3045.52 | Closed | -563.09
PRJ-202505-0114 | 2025-05-03 | 2025-05-06 | Residential | Install - New Construction | Derek Collins | 7167.42 | 4830.22 | 4744.74 | 4744.74 | Closed | -85.48
PRJ-202505-0115 | 2025-05-09 | 2025-05-13 | Residential | Install - Replacement | Derek Collins | 6652.24 | 4291.79 | 4109.09 | 4109.09 | Closed | -182.7
PRJ-202505-0116 | 2025-05-24 | 2025-05-28 | Residential | Service - Major Repair | Luis Martinez | 6627.92 | 3947.24 | 3945.4 | 3945.4 | Closed | -1.84
PRJ-202505-0117 | 2025-05-20 | 2025-05-24 | Residential | Install - Replacement | Luis Martinez | 4239.83 | 2736.95 | 2728.52 | 2728.52 | Closed | -8.43
PRJ-202505-0118 | 2025-05-23 | 2025-06-17 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 42416.02 | 32743.23 | 34122.24 | 34122.24 | Closed | 1379.01
PRJ-202505-0119 | 2025-05-20 | 2025-06-04 | Light Commercial | Tenant Improvement | Carlos Vega | 27839.38 | 18490.55 | 19779.17 | 19779.17 | Closed | 1288.62
PRJ-202505-0120 | 2025-05-14 | 2025-06-14 | Light Commercial | Commercial RTU Replacement | Derek Collins | 23425.75 | 16325.66 | 16094 | 16094 | Closed | -231.66
PRJ-202505-0121 | 2025-05-18 | 2025-06-28 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 30415.72 | 22708.93 | 26287.7 | 26287.7 | Closed | 3578.77
PRJ-202505-0122 | 2025-05-12 | 2025-05-13 | Residential | Service - Major Repair | Derek Collins | 5623.5 | 3562.83 | 3062.71 | 3062.71 | Closed | -500.12
PRJ-202505-0123 | 2025-05-25 | 2025-05-28 | Residential | Service - Major Repair | Luis Martinez | 6609.6 | 4355.63 | 4294.92 | 4294.92 | Closed | -60.71
PRJ-202505-0124 | 2025-05-13 | 2025-05-16 | Residential | Install - Replacement | Brandon Shaw | 6598.71 | 4616.28 | 4382.84 | 4382.84 | Closed | -233.44
PRJ-202505-0125 | 2025-05-15 | 2025-05-16 | Residential | Install - Replacement | Carlos Vega | 4663.61 | 3014.67 | 3179.92 | 3179.92 | Closed | 165.25
PRJ-202506-0126 | 2025-06-06 | 2025-06-09 | Residential | Install - Replacement | Derek Collins | 5423.33 | 3451.7 | 3826.39 | 3826.39 | Closed | 374.69
PRJ-202506-0127 | 2025-06-17 | 2025-08-10 | Light Commercial | Commercial RTU Replacement | Derek Collins | 47730.66 | 36456.29 | 32805.24 | 32805.24 | Closed | -3651.05
PRJ-202506-0128 | 2025-06-25 | 2025-06-27 | Residential | Install - Replacement | Derek Collins | 7020.86 | 4988.42 | 4784.28 | 4784.28 | Closed | -204.14
PRJ-202506-0129 | 2025-06-20 | 2025-06-21 | Residential | Install - Replacement | Anthony Ruiz | 7610.98 | 4684.52 | 4549.03 | 4549.03 | Closed | -135.49
PRJ-202506-0130 | 2025-06-01 | 2025-06-05 | Residential | Install - Replacement | Derek Collins | 3711.77 | 2540.22 | 2530.23 | 2530.23 | Closed | -9.99
PRJ-202506-0131 | 2025-06-13 | 2025-06-28 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 27606.56 | 22289.86 | 19858.27 | 19858.27 | Closed | -2431.59
PRJ-202506-0132 | 2025-06-19 | 2025-06-21 | Residential | Install - New Construction | Luis Martinez | 7491.67 | 4958.29 | 4214.55 | 4214.55 | Closed | -743.74
PRJ-202506-0133 | 2025-06-24 | 2025-06-28 | Residential | Install - Replacement | Anthony Ruiz | 7608.01 | 4855.56 | 5223.41 | 5223.41 | Closed | 367.85
PRJ-202506-0134 | 2025-06-08 | 2025-06-12 | Residential | Install - Replacement | Anthony Ruiz | 3711.77 | 2092.94 | 2371.78 | 2371.78 | Closed | 278.84
PRJ-202506-0135 | 2025-06-19 | 2025-07-14 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 22873.79 | 16868.96 | 19533.85 | 19533.85 | Closed | 2664.89
PRJ-202506-0136 | 2025-06-02 | 2025-06-05 | Residential | Install - Replacement | Derek Collins | 7449.36 | 4794.85 | 4871.61 | 4871.61 | Closed | 76.76
PRJ-202506-0137 | 2025-06-11 | 2025-06-15 | Residential | Install - Replacement | Anthony Ruiz | 5774.48 | 4196.46 | 4705.69 | 4705.69 | Closed | 509.23
PRJ-202506-0138 | 2025-06-04 | 2025-06-05 | Residential | Install - Replacement | Derek Collins | 8317.34 | 5915.14 | 5836.85 | 5836.85 | Closed | -78.29
PRJ-202506-0139 | 2025-06-24 | 2025-07-23 | Light Commercial | Tenant Improvement | Anthony Ruiz | 33978.58 | 20518.34 | 23195.78 | 23195.78 | Closed | 2677.44
PRJ-202506-0140 | 2025-06-06 | 2025-07-13 | Light Commercial | Tenant Improvement | Carlos Vega | 32231.3 | 22369.91 | 21857.02 | 21857.02 | Closed | -512.89
PRJ-202506-0141 | 2025-06-17 | 2025-06-20 | Residential | Service - Major Repair | Anthony Ruiz | 8075.79 | 5127.99 | 5794.2 | 5794.2 | Closed | 666.21
PRJ-202506-0142 | 2025-06-25 | 2025-08-22 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 23866.5 | 16658.81 | 16830.12 | 16830.12 | Closed | 171.31
PRJ-202506-0143 | 2025-06-06 | 2025-06-07 | Residential | Install - Replacement | Derek Collins | 5727.85 | 3105 | 3253.3 | 3253.3 | Closed | 148.3
PRJ-202506-0144 | 2025-06-22 | 2025-06-26 | Residential | Service - Major Repair | Carlos Vega | 4050.56 | 2661.08 | 3099.17 | 3099.17 | Closed | 438.09
PRJ-202506-0145 | 2025-06-22 | 2025-06-24 | Residential | Install - New Construction | Brandon Shaw | 4717.49 | 3126.09 | 3195.04 | 3195.04 | Closed | 68.95
PRJ-202506-0146 | 2025-06-24 | 2025-06-27 | Residential | Install - Replacement | Carlos Vega | 7226.46 | 4640.34 | 4710.64 | 4710.64 | Closed | 70.3
PRJ-202506-0147 | 2025-06-19 | 2025-07-05 | Light Commercial | Tenant Improvement | Luis Martinez | 35325.82 | 21092.19 | 17928.36 | 17928.36 | Closed | -3163.83
PRJ-202506-0148 | 2025-06-02 | 2025-06-30 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 26393.46 | 16547.41 | 18131.7 | 18131.7 | Closed | 1584.29
PRJ-202506-0149 | 2025-06-03 | 2025-06-05 | Residential | Install - Replacement | Derek Collins | 8167.73 | 4790.13 | 5006.01 | 5006.01 | Closed | 215.88
PRJ-202506-0150 | 2025-06-12 | 2025-07-19 | Light Commercial | Commercial RTU Replacement | Derek Collins | 21811.68 | 17875.82 | 16708.55 | 16708.55 | Closed | -1167.27
PRJ-202506-0151 | 2025-06-10 | 2025-07-18 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 34724.38 | 25332.71 | 25396.93 | 25396.93 | Closed | 64.22
PRJ-202506-0152 | 2025-06-18 | 2025-07-11 | Light Commercial | Tenant Improvement | Carlos Vega | 24017.88 | 15096.85 | 14022.63 | 14022.63 | Closed | -1074.22
PRJ-202506-0153 | 2025-06-23 | 2025-06-25 | Residential | Service - Major Repair | Carlos Vega | 4574.62 | 2950.62 | 3083.19 | 3083.19 | Closed | 132.57
PRJ-202506-0154 | 2025-06-01 | 2025-06-02 | Residential | Install - Replacement | Carlos Vega | 7759.15 | 5093.96 | 6076.16 | 6076.16 | Closed | 982.2
PRJ-202507-0155 | 2025-07-10 | 2025-07-11 | Residential | Service - Major Repair | Anthony Ruiz | 7709.24 | 4972.54 | 5834.16 | 5834.16 | Closed | 861.62
PRJ-202507-0156 | 2025-07-18 | 2025-07-22 | Residential | Install - Replacement | Carlos Vega | 9051.44 | 5511.79 | 5060.68 | 5060.68 | Closed | -451.11
PRJ-202507-0157 | 2025-07-20 | 2025-08-25 | Light Commercial | Commercial Service | Derek Collins | 22851.89 | 15229.31 | 15198.63 | 15198.63 | Closed | -30.68
PRJ-202507-0158 | 2025-07-02 | 2025-07-03 | Residential | Install - New Construction | Brandon Shaw | 7277.31 | 4499.44 | 4060.29 | 4060.29 | Closed | -439.15
PRJ-202507-0159 | 2025-07-07 | 2025-07-11 | Residential | Install - Replacement | Luis Martinez | 9918.3 | 6957.65 | 6972.01 | 6972.01 | Closed | 14.36
PRJ-202507-0160 | 2025-07-13 | 2025-07-29 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 28251.41 | 18299.8 | 17044.93 | 17044.93 | Closed | -1254.87
PRJ-202507-0161 | 2025-07-22 | 2025-09-16 | Light Commercial | Commercial Service | Brandon Shaw | 40815.3 | 29738.18 | 27078.98 | 27078.98 | Closed | -2659.2
PRJ-202507-0162 | 2025-07-10 | 2025-07-12 | Residential | Install - Replacement | Carlos Vega | 5464.39 | 4219.48 | 3682.24 | 3682.24 | Closed | -537.24
PRJ-202507-0163 | 2025-07-18 | 2025-07-21 | Residential | Install - Replacement | Derek Collins | 5623.97 | 3807.84 | 3254.44 | 3254.44 | Closed | -553.4
PRJ-202507-0164 | 2025-07-05 | 2025-07-31 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 37953.77 | 27616.35 | 26681.5 | 26681.5 | Closed | -934.85
PRJ-202507-0165 | 2025-07-06 | 2025-07-07 | Residential | Install - New Construction | Derek Collins | 6263.57 | 3955.36 | 3696.59 | 3696.59 | Closed | -258.77
PRJ-202507-0166 | 2025-07-21 | 2025-07-23 | Residential | Install - New Construction | Carlos Vega | 6407.81 | 4009.94 | 3408.45 | 3408.45 | Closed | -601.49
PRJ-202507-0167 | 2025-07-23 | 2025-07-24 | Residential | Install - Replacement | Carlos Vega | 5851.2 | 3791.33 | 3796.42 | 3796.42 | Closed | 5.09
PRJ-202507-0168 | 2025-07-14 | 2025-07-16 | Residential | Install - Replacement | Brandon Shaw | 5390.73 | 3465.33 | 3229.49 | 3229.49 | Closed | -235.84
PRJ-202507-0169 | 2025-07-01 | 2025-07-02 | Residential | Install - Replacement | Anthony Ruiz | 6938.67 | 4425.16 | 4286.09 | 4286.09 | Closed | -139.07
PRJ-202507-0170 | 2025-07-16 | 2025-07-19 | Residential | Install - Replacement | Brandon Shaw | 6842.22 | 4484.16 | 4467.72 | 4467.72 | Closed | -16.44
PRJ-202507-0171 | 2025-07-09 | 2025-07-10 | Residential | Install - Replacement | Anthony Ruiz | 9595.49 | 6087.54 | 7285.08 | 7285.08 | Closed | 1197.54
PRJ-202507-0172 | 2025-07-18 | 2025-07-22 | Residential | Service - Major Repair | Derek Collins | 6160.82 | 3570.75 | 3582.22 | 3582.22 | Closed | 11.47
PRJ-202507-0173 | 2025-07-14 | 2025-07-15 | Residential | Service - Major Repair | Brandon Shaw | 8791.74 | 5465.88 | 5495.02 | 5495.02 | Closed | 29.14
PRJ-202507-0174 | 2025-07-11 | 2025-07-13 | Residential | Service - Major Repair | Brandon Shaw | 6654.34 | 3711.01 | 3419.47 | 3419.47 | Closed | -291.54
PRJ-202507-0175 | 2025-07-02 | 2025-08-27 | Light Commercial | Commercial Service | Anthony Ruiz | 27993.25 | 17427.89 | 16442.21 | 16442.21 | Closed | -985.68
PRJ-202507-0176 | 2025-07-08 | 2025-07-12 | Residential | Install - Replacement | Anthony Ruiz | 8346.12 | 4938.75 | 5137.5 | 5137.5 | Closed | 198.75
PRJ-202507-0177 | 2025-07-07 | 2025-08-11 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 36421.37 | 22717.99 | 24563.89 | 24563.89 | Closed | 1845.9
PRJ-202507-0178 | 2025-07-21 | 2025-07-22 | Residential | Install - New Construction | Luis Martinez | 6029.87 | 3948.83 | 4698.5 | 4698.5 | Closed | 749.67
PRJ-202507-0179 | 2025-07-14 | 2025-07-17 | Residential | Install - Replacement | Anthony Ruiz | 8848.99 | 5157.87 | 5868.76 | 5868.76 | Closed | 710.89
PRJ-202507-0180 | 2025-07-16 | 2025-07-19 | Residential | Install - Replacement | Derek Collins | 6979.31 | 4369.27 | 4432.56 | 4432.56 | Closed | 63.29
PRJ-202507-0181 | 2025-07-24 | 2025-07-26 | Residential | Install - New Construction | Carlos Vega | 6561.48 | 4252.69 | 3614.78 | 3614.78 | Closed | -637.91
PRJ-202507-0182 | 2025-07-25 | 2025-07-27 | Residential | Install - New Construction | Anthony Ruiz | 5840.52 | 3466.1 | 3730.08 | 3730.08 | Closed | 263.98
PRJ-202507-0183 | 2025-07-19 | 2025-08-30 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 39938.71 | 28280.02 | 29682.05 | 29682.05 | Closed | 1402.03
PRJ-202507-0184 | 2025-07-18 | 2025-09-09 | Light Commercial | Commercial Service | Carlos Vega | 27409.2 | 17540.69 | 19254.67 | 19254.67 | Closed | 1713.98
PRJ-202508-0185 | 2025-08-03 | 2025-08-06 | Residential | Service - Major Repair | Carlos Vega | 5273.33 | 3683.05 | 3140.9 | 3140.9 | Closed | -542.15
PRJ-202508-0186 | 2025-08-07 | 2025-09-25 | Light Commercial | Commercial RTU Replacement | Derek Collins | 32203.86 | 23205.03 | 20002.6 | 20002.6 | Closed | -3202.43
PRJ-202508-0187 | 2025-08-17 | 2025-08-19 | Residential | Install - Replacement | Derek Collins | 8518.89 | 4699.6 | 4283.29 | 4283.29 | Closed | -416.31
PRJ-202508-0188 | 2025-08-08 | 2025-08-12 | Residential | Install - Replacement | Anthony Ruiz | 6977.98 | 4333.16 | 4869.07 | 4869.07 | Closed | 535.91
PRJ-202508-0189 | 2025-08-23 | 2025-10-20 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 21979.91 | 13498.37 | 12702.13 | 12702.13 | Closed | -796.24
PRJ-202508-0190 | 2025-08-13 | 2025-09-11 | Light Commercial | Tenant Improvement | Derek Collins | 35739.44 | 20512.15 | 20041.23 | 20041.23 | Closed | -470.92
PRJ-202508-0191 | 2025-08-02 | 2025-08-28 | Light Commercial | Commercial RTU Replacement | Derek Collins | 40497.36 | 23676.94 | 22669.41 | 22669.41 | Closed | -1007.53
PRJ-202508-0192 | 2025-08-10 | 2025-08-12 | Residential | Install - Replacement | Brandon Shaw | 6776.28 | 4683.99 | 4359.55 | 4359.55 | Closed | -324.44
PRJ-202508-0193 | 2025-08-03 | 2025-08-05 | Residential | Install - New Construction | Derek Collins | 5903.77 | 3620.72 | 3797.83 | 3797.83 | Closed | 177.11
PRJ-202508-0194 | 2025-08-10 | 2025-08-11 | Residential | Install - New Construction | Carlos Vega | 5894.46 | 4530.06 | 4624.79 | 4624.79 | Closed | 94.73
PRJ-202508-0195 | 2025-08-09 | 2025-10-06 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 39048.62 | 25750.53 | 28537.73 | 28537.73 | Closed | 2787.2
PRJ-202508-0196 | 2025-08-08 | 2025-08-09 | Residential | Service - Major Repair | Derek Collins | 7258.1 | 4658.49 | 4111.3 | 4111.3 | Closed | -547.19
PRJ-202508-0197 | 2025-08-23 | 2025-08-26 | Residential | Install - New Construction | Carlos Vega | 6818.01 | 4515.87 | 5140.4 | 5140.4 | Closed | 624.53
PRJ-202508-0198 | 2025-08-18 | 2025-09-27 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 48833.15 | 34146.41 | 31407.98 | 31407.98 | Closed | -2738.43
PRJ-202508-0199 | 2025-08-19 | 2025-08-21 | Residential | Install - Replacement | Anthony Ruiz | 6507.32 | 4032.56 | 5256.87 | 5256.87 | Closed | 1224.31
PRJ-202508-0200 | 2025-08-07 | 2025-08-10 | Residential | Service - Major Repair | Luis Martinez | 4841.37 | 2784.62 | 2788.97 | 2788.97 | Closed | 4.35
PRJ-202508-0201 | 2025-08-07 | 2025-08-11 | Residential | Install - New Construction | Brandon Shaw | 6605.23 | 4478.15 | 4568.43 | 4568.43 | Closed | 90.28
PRJ-202508-0202 | 2025-08-23 | 2025-10-17 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 37189.45 | 23059.53 | 24320.64 | 24320.64 | Closed | 1261.11
PRJ-202508-0203 | 2025-08-13 | 2025-09-22 | Light Commercial | Tenant Improvement | Brandon Shaw | 33609.79 | 20876.31 | 23515.69 | 23515.69 | Closed | 2639.38
PRJ-202508-0204 | 2025-08-19 | 2025-08-21 | Residential | Install - Replacement | Anthony Ruiz | 5013.3 | 3666.91 | 3796.49 | 3796.49 | Closed | 129.58
PRJ-202508-0205 | 2025-08-22 | 2025-08-26 | Residential | Install - Replacement | Brandon Shaw | 5228.72 | 3172.25 | 3096.86 | 3096.86 | Closed | -75.39
PRJ-202508-0206 | 2025-08-09 | 2025-08-11 | Residential | Service - Major Repair | Brandon Shaw | 6001.24 | 4238.19 | 3937.39 | 3937.39 | Closed | -300.8
PRJ-202508-0207 | 2025-08-08 | 2025-08-28 | Light Commercial | Commercial RTU Replacement | Derek Collins | 28090.41 | 17260.08 | 17234.73 | 17234.73 | Closed | -25.35
PRJ-202508-0208 | 2025-08-04 | 2025-08-07 | Residential | Install - Replacement | Anthony Ruiz | 4504.44 | 3327.13 | 4055.49 | 4055.49 | Closed | 728.36
PRJ-202508-0209 | 2025-08-20 | 2025-08-21 | Residential | Install - Replacement | Luis Martinez | 6262.35 | 3491.98 | 4221.4 | 4221.4 | Closed | 729.42
PRJ-202508-0210 | 2025-08-25 | 2025-08-28 | Residential | Service - Major Repair | Anthony Ruiz | 4964.98 | 3138.68 | 3336.71 | 3336.71 | Closed | 198.03
PRJ-202508-0211 | 2025-08-18 | 2025-08-20 | Residential | Install - Replacement | Brandon Shaw | 4721.17 | 3047.38 | 3397.41 | 3397.41 | Closed | 350.03
PRJ-202508-0212 | 2025-08-25 | 2025-08-29 | Residential | Install - Replacement | Luis Martinez | 4686.32 | 3155.55 | 3143.26 | 3143.26 | Closed | -12.29
PRJ-202508-0213 | 2025-08-15 | 2025-08-17 | Residential | Install - New Construction | Anthony Ruiz | 7866.25 | 5590.68 | 6398.29 | 6398.29 | Closed | 807.61
PRJ-202508-0214 | 2025-08-20 | 2025-09-07 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 39435.21 | 27915.51 | 31713.9 | 31713.9 | Closed | 3798.39
PRJ-202509-0215 | 2025-09-21 | 2025-10-14 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 22610.31 | 17150.86 | 20493.39 | 20493.39 | Closed | 3342.53
PRJ-202509-0216 | 2025-09-15 | 2025-09-19 | Residential | Install - Replacement | Carlos Vega | 5597.09 | 3536.48 | 3359.3 | 3359.3 | Closed | -177.18
PRJ-202509-0217 | 2025-09-11 | 2025-09-13 | Residential | Install - Replacement | Anthony Ruiz | 5803.9 | 3313.71 | 3912.58 | 3912.58 | Closed | 598.87
PRJ-202509-0218 | 2025-09-19 | 2025-10-11 | Light Commercial | Commercial Service | Carlos Vega | 38129.03 | 25935.74 | 24774.29 | 24774.29 | Closed | -1161.45
PRJ-202509-0219 | 2025-09-03 | 2025-09-04 | Residential | Install - Replacement | Brandon Shaw | 5024.98 | 2779.8 | 2846.64 | 2846.64 | Closed | 66.84
PRJ-202509-0220 | 2025-09-06 | 2025-11-03 | Light Commercial | Commercial Service | Carlos Vega | 27422.26 | 19282.93 | 21806.21 | 21806.21 | Closed | 2523.28
PRJ-202509-0221 | 2025-09-21 | 2025-09-23 | Residential | Install - New Construction | Luis Martinez | 7064.01 | 4699.45 | 5112.14 | 5112.14 | Closed | 412.69
PRJ-202509-0222 | 2025-09-11 | 2025-09-15 | Residential | Install - New Construction | Derek Collins | 7362.01 | 4806.64 | 4628.98 | 4628.98 | Closed | -177.66
PRJ-202509-0223 | 2025-09-03 | 2025-10-05 | Light Commercial | Commercial Service | Brandon Shaw | 52928.62 | 31473.93 | 32178.89 | 32178.89 | Closed | 704.96
PRJ-202509-0224 | 2025-09-20 | 2025-09-24 | Residential | Service - Major Repair | Brandon Shaw | 7794.72 | 5036.12 | 4330.19 | 4330.19 | Closed | -705.93
PRJ-202509-0225 | 2025-09-11 | 2025-09-12 | Residential | Install - Replacement | Derek Collins | 6621.02 | 4618.29 | 4372.08 | 4372.08 | Closed | -246.21
PRJ-202509-0226 | 2025-09-20 | 2025-09-21 | Residential | Service - Major Repair | Carlos Vega | 5123.35 | 3066.18 | 2893.27 | 2893.27 | Closed | -172.91
PRJ-202509-0227 | 2025-09-06 | 2025-09-08 | Residential | Service - Major Repair | Luis Martinez | 7738.69 | 4489.42 | 5172.31 | 5172.31 | Closed | 682.89
PRJ-202509-0228 | 2025-09-21 | 2025-09-23 | Residential | Install - Replacement | Anthony Ruiz | 7614.15 | 4783.5 | 4352.04 | 4352.04 | Closed | -431.46
PRJ-202509-0229 | 2025-09-14 | 2025-11-05 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 31546.22 | 22776.63 | 25340.05 | 25340.05 | Closed | 2563.42
PRJ-202509-0230 | 2025-09-04 | 2025-10-31 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 34287.9 | 20234.29 | 20172.83 | 20172.83 | Closed | -61.46
PRJ-202509-0231 | 2025-09-18 | 2025-09-22 | Residential | Install - Replacement | Derek Collins | 5556.67 | 3279.35 | 3610.34 | 3610.34 | Closed | 330.99
PRJ-202509-0232 | 2025-09-07 | 2025-09-28 | Light Commercial | Commercial RTU Replacement | Derek Collins | 35760.77 | 23084.76 | 24401.76 | 24401.76 | Closed | 1317
PRJ-202509-0233 | 2025-09-12 | 2025-10-24 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 54500.76 | 32794.47 | 36621.24 | 36621.24 | Closed | 3826.77
PRJ-202509-0234 | 2025-09-05 | 2025-09-08 | Residential | Install - Replacement | Carlos Vega | 6188.52 | 4076.12 | 4510.83 | 4510.83 | Closed | 434.71
PRJ-202509-0235 | 2025-09-04 | 2025-09-05 | Residential | Service - Major Repair | Anthony Ruiz | 5873.15 | 4082.97 | 3790.07 | 3790.07 | Closed | -292.9
PRJ-202509-0236 | 2025-09-07 | 2025-09-09 | Residential | Service - Major Repair | Derek Collins | 5073.49 | 3257.1 | 3643.12 | 3643.12 | Closed | 386.02
PRJ-202509-0237 | 2025-09-04 | 2025-09-08 | Residential | Install - New Construction | Anthony Ruiz | 5952.47 | 4088.16 | 5315.38 | 5315.38 | Closed | 1227.22
PRJ-202509-0238 | 2025-09-11 | 2025-10-16 | Light Commercial | Tenant Improvement | Brandon Shaw | 32762.17 | 20519.43 | 20281.31 | 20281.31 | Closed | -238.12
PRJ-202509-0239 | 2025-09-08 | 2025-09-11 | Residential | Install - Replacement | Luis Martinez | 8068.35 | 5111.43 | 6316.67 | 6316.67 | Closed | 1205.24
PRJ-202509-0240 | 2025-09-08 | 2025-09-10 | Residential | Service - Major Repair | Brandon Shaw | 5301.5 | 3389.9 | 3625.03 | 3625.03 | Closed | 235.13
PRJ-202509-0241 | 2025-09-25 | 2025-11-15 | Light Commercial | Commercial RTU Replacement | Derek Collins | 32986.38 | 20929.39 | 22438.34 | 22438.34 | Closed | 1508.95
PRJ-202509-0242 | 2025-09-11 | 2025-10-16 | Light Commercial | Tenant Improvement | Brandon Shaw | 42139.12 | 27361.84 | 23940.71 | 23940.71 | Closed | -3421.13
PRJ-202509-0243 | 2025-09-21 | 2025-09-25 | Residential | Install - New Construction | Anthony Ruiz | 6444.41 | 4262.84 | 4577.71 | 4577.71 | Closed | 314.87
PRJ-202509-0244 | 2025-09-22 | 2025-09-23 | Residential | Install - Replacement | Luis Martinez | 7026.6 | 4787.87 | 4592.19 | 4592.19 | Closed | -195.68
PRJ-202510-0245 | 2025-10-08 | 2025-10-11 | Residential | Install - Replacement | Derek Collins | 7006.62 | 4357.77 | 4298.86 | 4298.86 | Closed | -58.91
PRJ-202510-0246 | 2025-10-04 | 2025-10-06 | Residential | Install - New Construction | Brandon Shaw | 7579.7 | 4078.65 | 4029.69 | 4029.69 | Closed | -48.96
PRJ-202510-0247 | 2025-10-18 | 2025-10-19 | Residential | Install - New Construction | Derek Collins | 7176.29 | 4721.74 | 4936.83 | 4936.83 | Closed | 215.09
PRJ-202510-0248 | 2025-10-19 | 2025-10-22 | Residential | Install - New Construction | Carlos Vega | 6683.94 | 4219.11 | 4326.46 | 4326.46 | Closed | 107.35
PRJ-202510-0249 | 2025-10-23 | 2025-11-20 | Light Commercial | Commercial Service | Derek Collins | 24876.51 | 17876.09 | 18072.93 | 18072.93 | Closed | 196.84
PRJ-202510-0250 | 2025-10-23 | 2025-10-26 | Residential | Install - Replacement | Brandon Shaw | 5917.39 | 3916.74 | 4037.93 | 4037.93 | Closed | 121.19
PRJ-202510-0251 | 2025-10-16 | 2025-11-07 | Light Commercial | Tenant Improvement | Carlos Vega | 13256.31 | 9117.36 | 10049.88 | 10049.88 | Closed | 932.52
PRJ-202510-0252 | 2025-10-05 | 2025-10-06 | Residential | Service - Major Repair | Anthony Ruiz | 5384.57 | 3306.37 | 3068.06 | 3068.06 | Closed | -238.31
PRJ-202510-0253 | 2025-10-06 | 2025-10-22 | Light Commercial | Commercial Service | Derek Collins | 17044.05 | 10246.67 | 10441.33 | 10441.33 | Closed | 194.66
PRJ-202510-0254 | 2025-10-10 | 2025-10-11 | Residential | Install - Replacement | Carlos Vega | 8475.34 | 5433.98 | 6295.08 | 6295.08 | Closed | 861.1
PRJ-202510-0255 | 2025-10-17 | 2025-12-09 | Light Commercial | Commercial Service | Brandon Shaw | 24001.51 | 15738.88 | 14164.07 | 14164.07 | Closed | -1574.81
PRJ-202510-0256 | 2025-10-13 | 2025-12-07 | Light Commercial | Tenant Improvement | Anthony Ruiz | 36263 | 24901.23 | 32382.49 | 32382.49 | Closed | 7481.26
PRJ-202510-0257 | 2025-10-14 | 2025-12-10 | Light Commercial | Tenant Improvement | Derek Collins | 42815.76 | 26418.24 | 27161.56 | 27161.56 | Closed | 743.32
PRJ-202510-0258 | 2025-10-15 | 2025-10-18 | Residential | Install - Replacement | Carlos Vega | 4827.76 | 3343.59 | 2842.05 | 2842.05 | Closed | -501.54
PRJ-202510-0259 | 2025-10-20 | 2025-11-27 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 34795.57 | 21519.3 | 26722.69 | 26722.69 | Closed | 5203.39
PRJ-202510-0260 | 2025-10-10 | 2025-12-02 | Light Commercial | Tenant Improvement | Carlos Vega | 30933.14 | 21039.44 | 24591.26 | 24591.26 | Closed | 3551.82
PRJ-202510-0261 | 2025-10-14 | 2025-12-05 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 24308.11 | 17156.96 | 17997.78 | 17997.78 | Closed | 840.82
PRJ-202510-0262 | 2025-10-18 | 2025-10-22 | Residential | Install - Replacement | Derek Collins | 6333.19 | 3910.2 | 3984.05 | 3984.05 | Closed | 73.85
PRJ-202510-0263 | 2025-10-22 | 2025-10-24 | Residential | Service - Major Repair | Anthony Ruiz | 6468.46 | 3905.69 | 4592.77 | 4592.77 | Closed | 687.08
PRJ-202510-0264 | 2025-10-20 | 2025-11-08 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 47090.06 | 35828.97 | 41053.99 | 41053.99 | Closed | 5225.02
PRJ-202510-0265 | 2025-10-23 | 2025-10-27 | Residential | Install - New Construction | Derek Collins | 3711.77 | 2633.83 | 2536.21 | 2536.21 | Closed | -97.62
PRJ-202510-0266 | 2025-10-09 | 2025-10-10 | Residential | Service - Major Repair | Luis Martinez | 3857.69 | 2476.23 | 2319.11 | 2319.11 | Closed | -157.12
PRJ-202511-0267 | 2025-11-09 | 2025-11-10 | Residential | Service - Major Repair | Derek Collins | 6900.55 | 4372.08 | 4441.3 | 4441.3 | Closed | 69.22
PRJ-202511-0268 | 2025-11-22 | 2025-11-24 | Residential | Install - Replacement | Luis Martinez | 4033.07 | 2286.35 | 2360.4 | 2360.4 | Closed | 74.05
PRJ-202511-0269 | 2025-11-23 | 2025-11-27 | Residential | Install - Replacement | Anthony Ruiz | 5546.13 | 3420.46 | 3868.91 | 3868.91 | Closed | 448.45
PRJ-202511-0270 | 2025-11-22 | 2025-11-23 | Residential | Install - Replacement | Derek Collins | 6751.25 | 4794.4 | 4904.43 | 4904.43 | Closed | 110.03
PRJ-202511-0271 | 2025-11-15 | 2025-11-17 | Residential | Service - Major Repair | Derek Collins | 9618.73 | 6450.25 | 6351.71 | 6351.71 | Closed | -98.54
PRJ-202511-0272 | 2025-11-16 | 2025-11-20 | Residential | Install - New Construction | Brandon Shaw | 9008.47 | 5517.5 | 4890.13 | 4890.13 | Closed | -627.37
PRJ-202511-0273 | 2025-11-11 | 2025-11-13 | Residential | Install - New Construction | Anthony Ruiz | 7967.63 | 4917.1 | 6035.5 | 6035.5 | Closed | 1118.4
PRJ-202511-0274 | 2025-11-14 | 2025-12-27 | Light Commercial | Tenant Improvement | Anthony Ruiz | 43019.67 | 31382.61 | 30838.06 | 30838.06 | Closed | -544.55
PRJ-202511-0275 | 2025-11-11 | 2025-11-14 | Residential | Service - Major Repair | Luis Martinez | 7197.92 | 4507.03 | 4776.67 | 4776.67 | Closed | 269.64
PRJ-202511-0276 | 2025-11-20 | 2026-01-13 | Light Commercial | Commercial Service | Brandon Shaw | 33963.62 | 23251.16 | 23287.7 | 23287.7 | Closed | 36.54
PRJ-202511-0277 | 2025-11-06 | 2025-11-09 | Residential | Install - New Construction | Derek Collins | 4680.49 | 2997.31 | 2560.02 | 2560.02 | Closed | -437.29
PRJ-202511-0278 | 2025-11-20 | 2026-01-13 | Light Commercial | Commercial Service | Brandon Shaw | 31585.08 | 21033.67 | 23040.36 | 23040.36 | Closed | 2006.69
PRJ-202511-0279 | 2025-11-02 | 2025-11-04 | Residential | Install - Replacement | Luis Martinez | 7767.91 | 4841.36 | 5492.57 | 5492.57 | Closed | 651.21
PRJ-202511-0280 | 2025-11-06 | 2025-11-08 | Residential | Install - Replacement | Anthony Ruiz | 4349.02 | 2661.68 | 2262.43 | 2262.43 | Closed | -399.25
PRJ-202511-0281 | 2025-11-06 | 2025-12-27 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 32479.74 | 22730.1 | 22486.36 | 22486.36 | Closed | -243.74
PRJ-202511-0282 | 2025-11-12 | 2025-11-15 | Residential | Service - Major Repair | Brandon Shaw | 7712.92 | 5233.65 | 5115.47 | 5115.47 | Closed | -118.18
PRJ-202511-0283 | 2025-11-06 | 2025-11-25 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 33229.61 | 27248.28 | 30845.85 | 30845.85 | Closed | 3597.57
PRJ-202511-0284 | 2025-11-13 | 2025-11-14 | Residential | Service - Major Repair | Luis Martinez | 5567.49 | 3158.4 | 3187.13 | 3187.13 | Closed | 28.73
PRJ-202511-0285 | 2025-11-05 | 2025-12-17 | Light Commercial | Commercial Service | Carlos Vega | 46186.71 | 29420.04 | 37469.25 | 37469.25 | Closed | 8049.21
PRJ-202511-0286 | 2025-11-11 | 2025-11-14 | Residential | Install - New Construction | Derek Collins | 7076.89 | 4969.24 | 5047.81 | 5047.81 | Closed | 78.57
PRJ-202511-0287 | 2025-11-09 | 2025-11-11 | Residential | Service - Major Repair | Carlos Vega | 7206.14 | 4144.28 | 3836.7 | 3836.7 | Closed | -307.58
PRJ-202511-0288 | 2025-11-07 | 2025-11-28 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 32806.72 | 23521.55 | 25312.39 | 25312.39 | Closed | 1790.84
PRJ-202511-0289 | 2025-11-01 | 2025-11-02 | Residential | Service - Major Repair | Anthony Ruiz | 6089.83 | 4110.18 | 4258.86 | 4258.86 | Closed | 148.68
PRJ-202511-0290 | 2025-11-16 | 2025-12-06 | Light Commercial | Commercial Service | Brandon Shaw | 40249.84 | 26865.58 | 29359.59 | 29359.59 | Closed | 2494.01
PRJ-202512-0291 | 2025-12-09 | 2026-01-31 | Light Commercial | Commercial RTU Replacement | Derek Collins | 21471.08 | 12335.17 | 11114.58 | 11114.58 | Closed | -1220.59
PRJ-202512-0292 | 2025-12-20 | 2025-12-21 | Residential | Install - Replacement | Luis Martinez | 7016.11 | 4311.71 | 4824.69 | 4824.69 | Closed | 512.98
PRJ-202512-0293 | 2025-12-15 | 2025-12-16 | Residential | Install - New Construction | Luis Martinez | 6427.39 | 3733.51 | 3597.64 | 3597.64 | Closed | -135.87
PRJ-202512-0294 | 2025-12-02 | 2025-12-04 | Residential | Install - New Construction | Derek Collins | 5179.28 | 3264.35 | 2903.98 | 2903.98 | Closed | -360.37
PRJ-202512-0295 | 2025-12-10 | 2025-12-11 | Residential | Install - Replacement | Anthony Ruiz | 6069.64 | 3924.24 | 3967.28 | 3967.28 | Closed | 43.04
PRJ-202512-0296 | 2025-12-18 | 2025-12-19 | Residential | Install - Replacement | Derek Collins | 6531.33 | 4088.97 | 4195.79 | 4195.79 | Closed | 106.82
PRJ-202512-0297 | 2025-12-03 | 2025-12-04 | Residential | Install - Replacement | Derek Collins | 3711.77 | 2131.57 | 2328.93 | 2328.93 | Closed | 197.36
PRJ-202512-0298 | 2025-12-02 | 2025-12-03 | Residential | Install - Replacement | Anthony Ruiz | 5146.34 | 2896.03 | 2899.07 | 2899.07 | Closed | 3.04
PRJ-202512-0299 | 2025-12-12 | 2025-12-14 | Residential | Install - Replacement | Luis Martinez | 6411.74 | 3920.16 | 4320.44 | 4320.44 | Closed | 400.28
PRJ-202512-0300 | 2025-12-23 | 2026-01-07 | Light Commercial | Commercial RTU Replacement | Derek Collins | 15000.16 | 10428.51 | 9281.17 | 9281.17 | Closed | -1147.34
PRJ-202512-0301 | 2025-12-25 | 2025-12-27 | Residential | Install - Replacement | Anthony Ruiz | 8360.08 | 5717.02 | 6505.54 | 6505.54 | Closed | 788.52
PRJ-202512-0302 | 2025-12-06 | 2025-12-09 | Residential | Service - Major Repair | Anthony Ruiz | 5502.04 | 3858.88 | 4544.42 | 4544.42 | Closed | 685.54
PRJ-202512-0303 | 2025-12-18 | 2025-12-22 | Residential | Install - Replacement | Carlos Vega | 3711.77 | 2279.16 | 2494.35 | 2494.35 | Closed | 215.19
PRJ-202512-0304 | 2025-12-24 | 2025-12-27 | Residential | Install - Replacement | Derek Collins | 7917.52 | 5343.87 | 4995.3 | 4995.3 | Closed | -348.57
PRJ-202512-0305 | 2025-12-22 | 2025-12-25 | Residential | Install - Replacement | Derek Collins | 6442.8 | 4289.5 | 4665.68 | 4665.68 | Closed | 376.18
PRJ-202512-0306 | 2025-12-03 | 2026-01-04 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 36152.52 | 23153.91 | 27011.31 | 27011.31 | Closed | 3857.4
PRJ-202512-0307 | 2025-12-23 | 2025-12-24 | Residential | Service - Major Repair | Brandon Shaw | 3711.77 | 2567.74 | 2944.56 | 2944.56 | Closed | 376.82
PRJ-202512-0308 | 2025-12-07 | 2025-12-10 | Residential | Install - Replacement | Derek Collins | 5891.45 | 3890.99 | 3855.22 | 3855.22 | Closed | -35.77
PRJ-202512-0309 | 2025-12-16 | 2025-12-19 | Residential | Install - Replacement | Carlos Vega | 5621.65 | 3754.19 | 3443.19 | 3443.19 | Closed | -311
PRJ-202512-0310 | 2025-12-05 | 2026-01-25 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 34554.62 | 24255.5 | 25993.57 | 25993.57 | Closed | 1738.07
PRJ-202512-0311 | 2025-12-17 | 2025-12-18 | Residential | Install - Replacement | Derek Collins | 3775.44 | 2445.11 | 2571.63 | 2571.63 | Closed | 126.52
PRJ-202512-0312 | 2025-12-18 | 2025-12-19 | Residential | Service - Major Repair | Luis Martinez | 7003.4 | 4147.89 | 4742.4 | 4742.4 | Closed | 594.51
PRJ-202601-0313 | 2026-01-17 | 2026-03-06 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 26406.95 | 18582.71 | 20387.74 | 20387.74 | Closed | 1805.03
PRJ-202601-0314 | 2026-01-15 | 2026-01-19 | Residential | Install - New Construction | Carlos Vega | 7255.15 | 4917.94 | 5649.68 | 5649.68 | Closed | 731.74
PRJ-202601-0315 | 2026-01-10 | 2026-02-10 | Light Commercial | Tenant Improvement | Derek Collins | 13256.31 | 8539.9 | 8441.81 | 8441.81 | Closed | -98.09
PRJ-202601-0316 | 2026-01-08 | 2026-01-11 | Residential | Service - Major Repair | Anthony Ruiz | 8401.91 | 4819.49 | 5710.32 | 5710.32 | Closed | 890.83
PRJ-202601-0317 | 2026-01-07 | 2026-02-22 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 26686.36 | 17713.87 | 19199.93 | 19199.93 | Closed | 1486.06
PRJ-202601-0318 | 2026-01-03 | 2026-01-18 | Light Commercial | Tenant Improvement | Carlos Vega | 37072.48 | 29707.97 | 29551.83 | 29551.83 | Closed | -156.14
PRJ-202601-0319 | 2026-01-01 | 2026-01-02 | Residential | Service - Major Repair | Derek Collins | 8214.86 | 5079.63 | 4935.97 | 4935.97 | Closed | -143.66
PRJ-202601-0320 | 2026-01-14 | 2026-02-02 | Light Commercial | Tenant Improvement | Anthony Ruiz | 34187.68 | 24784.01 | 23945.28 | 23945.28 | Closed | -838.73
PRJ-202601-0321 | 2026-01-14 | 2026-01-15 | Residential | Install - New Construction | Anthony Ruiz | 4631 | 3036.4 | 3601.8 | 3601.8 | Closed | 565.4
PRJ-202601-0322 | 2026-01-05 | 2026-01-06 | Residential | Install - New Construction | Derek Collins | 5402.43 | 3765.61 | 3805.1 | 3805.1 | Closed | 39.49
PRJ-202601-0323 | 2026-01-17 | 2026-02-19 | Light Commercial | Commercial Service | Brandon Shaw | 42663.77 | 30310.21 | 30810.24 | 30810.24 | Closed | 500.03
PRJ-202601-0324 | 2026-01-02 | 2026-02-25 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 22890.83 | 13930.33 | 12281.13 | 12281.13 | Closed | -1649.2
PRJ-202601-0325 | 2026-01-08 | 2026-02-06 | Light Commercial | Commercial RTU Replacement | Derek Collins | 17165.78 | 12262.6 | 12544.17 | 12544.17 | Closed | 281.57
PRJ-202601-0326 | 2026-01-20 | 2026-01-21 | Residential | Install - New Construction | Derek Collins | 5130.69 | 3499.66 | 3609.68 | 3609.68 | Closed | 110.02
PRJ-202601-0327 | 2026-01-23 | 2026-01-24 | Residential | Service - Major Repair | Derek Collins | 7844.85 | 4244.69 | 3808.67 | 3808.67 | Closed | -436.02
PRJ-202601-0328 | 2026-01-13 | 2026-01-14 | Residential | Install - Replacement | Luis Martinez | 5290.37 | 3581.97 | 3625.28 | 3625.28 | Closed | 43.31
PRJ-202601-0329 | 2026-01-06 | 2026-02-01 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 33169.78 | 20307.34 | 24502.85 | 24502.85 | Closed | 4195.51
PRJ-202601-0330 | 2026-01-19 | 2026-02-07 | Light Commercial | Tenant Improvement | Carlos Vega | 33258.58 | 20459.02 | 22341.7 | 22341.7 | Closed | 1882.68
PRJ-202601-0331 | 2026-01-19 | 2026-03-07 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 13256.31 | 10323.81 | 9908.69 | 9908.69 | Closed | -415.12
PRJ-202601-0332 | 2026-01-16 | 2026-01-17 | Residential | Install - Replacement | Derek Collins | 7468.84 | 4547.27 | 4291.85 | 4291.85 | Closed | -255.42
PRJ-202602-0333 | 2026-02-11 | 2026-02-14 | Residential | Service - Major Repair | Anthony Ruiz | 5602.87 | 3946.16 | 4900.82 | 4900.82 | Closed | 954.66
PRJ-202602-0334 | 2026-02-24 | 2026-02-28 | Residential | Service - Major Repair | Luis Martinez | 6724.35 | 4594.11 | 5309.12 | 5309.12 | Closed | 715.01
PRJ-202602-0335 | 2026-02-24 | 2026-02-28 | Residential | Install - New Construction | Derek Collins | 6618.07 | 4426.55 | 4337.92 | 4337.92 | Closed | -88.63
PRJ-202602-0336 | 2026-02-02 | 2026-02-06 | Residential | Install - Replacement | Carlos Vega | 6127.79 | 4385.96 | 4587.45 | 4587.45 | Closed | 201.49
PRJ-202602-0337 | 2026-02-19 | 2026-02-22 | Residential | Install - Replacement | Luis Martinez | 5817.79 | 3132.86 | 3578.52 | 3578.52 | Closed | 445.66
PRJ-202602-0338 | 2026-02-09 | 2026-02-11 | Residential | Install - Replacement | Carlos Vega | 7734.42 | 5114.53 | 4985.08 | 4985.08 | Closed | -129.45
PRJ-202602-0339 | 2026-02-06 | 2026-03-08 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 18849.21 | 13476.39 | 15229.61 | 15229.61 | Closed | 1753.22
PRJ-202602-0340 | 2026-02-19 | 2026-02-22 | Residential | Install - Replacement | Carlos Vega | 7556.21 | 4354.98 | 4510.63 | 4510.63 | Closed | 155.65
PRJ-202602-0341 | 2026-02-19 | 2026-02-20 | Residential | Install - Replacement | Brandon Shaw | 6153.21 | 3246.22 | 3159.1 | 3159.1 | Closed | -87.12
PRJ-202602-0342 | 2026-02-03 | 2026-02-04 | Residential | Install - New Construction | Carlos Vega | 7054.11 | 4203.97 | 4166.74 | 4166.74 | Closed | -37.23
PRJ-202602-0343 | 2026-02-09 | 2026-02-10 | Residential | Install - Replacement | Derek Collins | 6302.14 | 4132.48 | 3646.14 | 3646.14 | Closed | -486.34
PRJ-202602-0344 | 2026-02-06 | 2026-02-09 | Residential | Install - Replacement | Luis Martinez | 6661.93 | 5148.54 | 5726.4 | 5726.4 | Closed | 577.86
PRJ-202602-0345 | 2026-02-02 | 2026-02-23 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 38366.12 | 23726.78 | 27683.17 | 27683.17 | Closed | 3956.39
PRJ-202602-0346 | 2026-02-05 | 2026-02-08 | Residential | Service - Major Repair | Derek Collins | 7482.53 | 4920.57 | 4988.88 | 4988.88 | Closed | 68.31
PRJ-202602-0347 | 2026-02-07 | 2026-03-07 | Light Commercial | Tenant Improvement | Derek Collins | 20129.23 | 13203.7 | 12438.11 | 12438.11 | Closed | -765.59
PRJ-202602-0348 | 2026-02-18 | 2026-02-20 | Residential | Install - Replacement | Anthony Ruiz | 5272.25 | 3555.59 | 4217.52 | 4217.52 | Closed | 661.93
PRJ-202602-0349 | 2026-02-18 | 2026-02-21 | Residential | Install - Replacement | Derek Collins | 5033.81 | 3317.84 | 3381.51 | 3381.51 | Closed | 63.67
PRJ-202602-0350 | 2026-02-10 | 2026-02-13 | Residential | Service - Major Repair | Brandon Shaw | 6695.46 | 4336.85 | 3678.71 | 3678.71 | Closed | -658.14
PRJ-202602-0351 | 2026-02-09 | 2026-03-27 | Light Commercial | Commercial Service | Anthony Ruiz | 36869.94 | 20990.65 | 20944.25 | 20944.25 | Closed | -46.4
PRJ-202602-0352 | 2026-02-05 | 2026-02-06 | Residential | Install - Replacement | Luis Martinez | 6680.75 | 4532.36 | 4997.56 | 4997.56 | Closed | 465.2
PRJ-202602-0353 | 2026-02-17 | 2026-02-21 | Residential | Install - Replacement | Brandon Shaw | 6747.39 | 4577.75 | 4549.19 | 4549.19 | Closed | -28.56
PRJ-202602-0354 | 2026-02-23 | 2026-02-27 | Residential | Install - Replacement | Luis Martinez | 6557.52 | 4244.1 | 4590.45 | 4590.45 | Closed | 346.35
PRJ-202602-0355 | 2026-02-02 | 2026-02-05 | Residential | Service - Major Repair | Anthony Ruiz | 6300.05 | 4158.42 | 3694.13 | 3694.13 | Closed | -464.29
PRJ-202603-0356 | 2026-03-21 | 2026-03-24 | Residential | Install - Replacement | Luis Martinez | 7566.55 | 4594.6 | 5192.37 | 5192.37 | Closed | 597.77
PRJ-202603-0357 | 2026-03-12 | 2026-04-29 | Light Commercial | Tenant Improvement | Anthony Ruiz | 42995.81 | 29270.95 | 31869.04 | 31869.04 | Closed | 2598.09
PRJ-202603-0358 | 2026-03-18 | 2026-04-01 | Light Commercial | Tenant Improvement | Anthony Ruiz | 14798.29 | 10821.11 | 10300.56 | 10300.56 | Closed | -520.55
PRJ-202603-0359 | 2026-03-21 | 2026-03-24 | Residential | Install - New Construction | Anthony Ruiz | 7425.39 | 4973.29 | 5847.9 | 5847.9 | Closed | 874.61
PRJ-202603-0360 | 2026-03-14 | 2026-03-17 | Residential | Install - New Construction | Anthony Ruiz | 8129.37 | 5877.08 | 5743.2 | 5743.2 | Closed | -133.88
PRJ-202603-0361 | 2026-03-23 | 2026-03-24 | Residential | Install - Replacement | Carlos Vega | 6333.79 | 3839.17 | 3370.87 | 3370.87 | Closed | -468.3
PRJ-202603-0362 | 2026-03-18 | 2026-04-27 | Light Commercial | Tenant Improvement | Derek Collins | 44870.29 | 31937.09 | 34065.7 | 34065.7 | Closed | 2128.61
PRJ-202603-0363 | 2026-03-16 | 2026-03-18 | Residential | Install - New Construction | Luis Martinez | 8165.36 | 5288.71 | 5797.03 | 5797.03 | Closed | 508.32
PRJ-202603-0364 | 2026-03-13 | 2026-03-14 | Residential | Install - Replacement | Carlos Vega | 5829.96 | 3702.03 | 4501.96 | 4501.96 | Closed | 799.93
PRJ-202603-0365 | 2026-03-02 | 2026-03-20 | Light Commercial | Tenant Improvement | Derek Collins | 33660.19 | 18867.93 | 18553.88 | 18553.88 | Closed | -314.05
PRJ-202603-0366 | 2026-03-21 | 2026-05-03 | Light Commercial | Tenant Improvement | Brandon Shaw | 22122.46 | 14841.97 | 15743.89 | 15743.89 | Closed | 901.92
PRJ-202603-0367 | 2026-03-25 | 2026-03-26 | Residential | Install - Replacement | Brandon Shaw | 5556.07 | 3411.91 | 2769.8 | 2769.8 | Closed | -642.11
PRJ-202603-0368 | 2026-03-17 | 2026-04-10 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 31717.24 | 25020.03 | 25397.6 | 25397.6 | Closed | 377.57
PRJ-202603-0369 | 2026-03-14 | 2026-03-16 | Residential | Install - Replacement | Derek Collins | 5468.4 | 3739.83 | 3571.25 | 3571.25 | Closed | -168.58
PRJ-202603-0370 | 2026-03-04 | 2026-03-08 | Residential | Install - Replacement | Luis Martinez | 6845.21 | 4337.17 | 4697.94 | 4697.94 | Closed | 360.77
PRJ-202603-0371 | 2026-03-19 | 2026-03-22 | Residential | Install - Replacement | Anthony Ruiz | 5892.29 | 3575.22 | 4386.25 | 4386.25 | Closed | 811.03
PRJ-202603-0372 | 2026-03-19 | 2026-03-21 | Residential | Service - Major Repair | Carlos Vega | 4814.71 | 3573.35 | 3898.63 | 3898.63 | Closed | 325.28
PRJ-202603-0373 | 2026-03-11 | 2026-03-15 | Residential | Install - Replacement | Carlos Vega | 6810.12 | 4227.54 | 3593.41 | 3593.41 | Closed | -634.13
PRJ-202603-0374 | 2026-03-23 | 2026-03-24 | Residential | Install - Replacement | Carlos Vega | 8153.28 | 5468.67 | 5095.21 | 5095.21 | Closed | -373.46
PRJ-202603-0375 | 2026-03-08 | 2026-03-12 | Residential | Install - Replacement | Brandon Shaw | 5666 | 3753.8 | 3003.04 | 3003.04 | Closed | -750.76
PRJ-202603-0376 | 2026-03-01 | 2026-04-29 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 33473.45 | 25670.63 | 28092.28 | 28092.28 | Closed | 2421.65
PRJ-202603-0377 | 2026-03-18 | 2026-04-12 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 19218.5 | 14635.82 | 15399.81 | 15399.81 | Closed | 763.99
PRJ-202603-0378 | 2026-03-24 | 2026-03-27 | Residential | Service - Major Repair | Carlos Vega | 5404.45 | 3057.53 | 3292.84 | 3292.84 | Closed | 235.31
PRJ-202603-0379 | 2026-03-20 | 2026-03-21 | Residential | Install - Replacement | Luis Martinez | 7653.41 | 5267.64 | 6019.01 | 6019.01 | Closed | 751.37
PRJ-202603-0380 | 2026-03-13 | 2026-03-16 | Residential | Install - New Construction | Brandon Shaw | 7962.67 | 5002.42 | 5045.25 | 5045.25 | Closed | 42.83
PRJ-202604-0381 | 2026-04-02 | 2026-04-03 | Residential | Install - New Construction | Derek Collins | 5656.98 | 3866.67 | 3853.74 | 3853.74 | Closed | -12.93
PRJ-202604-0382 | 2026-04-20 | 2026-04-23 | Residential | Install - New Construction | Carlos Vega | 7557.68 | 5046.51 | 5436.46 | 5436.46 | Closed | 389.95
PRJ-202604-0383 | 2026-04-22 | 2026-04-25 | Residential | Install - Replacement | Anthony Ruiz | 4282.63 | 2860.56 | 2480.79 | 2480.79 | Closed | -379.77
PRJ-202604-0384 | 2026-04-04 | 2026-04-07 | Residential | Install - Replacement | Brandon Shaw | 5703.61 | 3937.21 | 3554.4 | 3554.4 | Closed | -382.81
PRJ-202604-0385 | 2026-04-18 | 2026-05-07 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 35651.45 | 20839.66 | 20897.06 | 20897.06 | Closed | 57.4
PRJ-202604-0386 | 2026-04-02 | 2026-04-26 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 40255.28 | 28947.75 | 35377.1 | 35377.1 | Closed | 6429.35
PRJ-202604-0387 | 2026-04-03 | 2026-05-19 | Light Commercial | Tenant Improvement | Brandon Shaw | 32813.39 | 23807.58 | 26007.21 | 26007.21 | Closed | 2199.63
PRJ-202604-0388 | 2026-04-20 | 2026-04-22 | Residential | Install - Replacement | Derek Collins | 6432.69 | 4012.75 | 3732.01 | 3732.01 | Closed | -280.74
PRJ-202604-0389 | 2026-04-22 | 2026-04-26 | Residential | Install - Replacement | Carlos Vega | 5721.68 | 3618.84 | 3737.17 | 3737.17 | Closed | 118.33
PRJ-202604-0390 | 2026-04-09 | 2026-06-05 | Light Commercial | Tenant Improvement | Carlos Vega | 32845.41 | 19291.02 | 17359.49 | 17359.49 | Closed | -1931.53
PRJ-202604-0391 | 2026-04-04 | 2026-04-05 | Residential | Install - Replacement | Carlos Vega | 8751.23 | 5285.67 | 5972.6 | 5972.6 | Closed | 686.93
PRJ-202604-0392 | 2026-04-24 | 2026-04-26 | Residential | Install - New Construction | Luis Martinez | 7639.83 | 4842.61 | 4751.54 | 4751.54 | Closed | -91.07
PRJ-202604-0393 | 2026-04-13 | 2026-04-16 | Residential | Install - Replacement | Anthony Ruiz | 5716.14 | 3471.09 | 3996.62 | 3996.62 | Closed | 525.53
PRJ-202604-0394 | 2026-04-05 | 2026-06-01 | Light Commercial | Commercial RTU Replacement | Derek Collins | 13256.31 | 9243.55 | 9470.87 | 9470.87 | Closed | 227.32
PRJ-202604-0395 | 2026-04-10 | 2026-04-13 | Residential | Service - Major Repair | Carlos Vega | 5832.31 | 3984.85 | 3857.83 | 3857.83 | Closed | -127.02
PRJ-202604-0396 | 2026-04-24 | 2026-05-27 | Light Commercial | Commercial Service | Carlos Vega | 26784.25 | 17836.01 | 19041.16 | 19041.16 | Closed | 1205.15
PRJ-202604-0397 | 2026-04-10 | 2026-04-13 | Residential | Install - Replacement | Luis Martinez | 6973.92 | 4883.98 | 5442.53 | 5442.53 | Closed | 558.55
PRJ-202604-0398 | 2026-04-13 | 2026-04-14 | Residential | Service - Major Repair | Derek Collins | 5221.28 | 3255.62 | 3197.99 | 3197.99 | Closed | -57.63
PRJ-202604-0399 | 2026-04-19 | 2026-04-23 | Residential | Install - New Construction | Luis Martinez | 6649.55 | 4311.48 | 4881.7 | 4881.7 | Closed | 570.22
PRJ-202604-0400 | 2026-04-13 | 2026-04-28 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 32453.58 | 23360.11 | 25946.11 | 25946.11 | Closed | 2586
PRJ-202604-0401 | 2026-04-19 | 2026-06-05 | Light Commercial | Commercial RTU Replacement | Derek Collins | 37251.28 | 25232.71 | 23221.54 | 23221.54 | Closed | -2011.17
PRJ-202604-0402 | 2026-04-18 | 2026-04-22 | Residential | Service - Major Repair | Derek Collins | 5643.33 | 3749.2 | 3876.63 | 3876.63 | Closed | 127.43
PRJ-202604-0403 | 2026-04-08 | 2026-04-09 | Residential | Install - Replacement | Luis Martinez | 6306.58 | 3520.67 | 4239.84 | 4239.84 | Closed | 719.17
PRJ-202604-0404 | 2026-04-12 | 2026-04-15 | Residential | Install - Replacement | Brandon Shaw | 7654.97 | 5656.95 | 5957.57 | 5957.57 | Closed | 300.62
PRJ-202604-0405 | 2026-04-22 | 2026-05-21 | Light Commercial | Tenant Improvement | Luis Martinez | 42603.67 | 31196.82 | 30642.39 | 30642.39 | Closed | -554.43
PRJ-202604-0406 | 2026-04-01 | 2026-04-05 | Residential | Install - Replacement | Anthony Ruiz | 5391.35 | 3113.45 | 3853.27 | 3853.27 | Closed | 739.82
PRJ-202604-0407 | 2026-04-23 | 2026-05-20 | Light Commercial | Commercial RTU Replacement | Derek Collins | 32474.59 | 25093.06 | 23329.22 | 23329.22 | Closed | -1763.84
PRJ-202604-0408 | 2026-04-14 | 2026-04-15 | Residential | Install - New Construction | Brandon Shaw | 6141.85 | 4084.36 | 4335.22 | 4335.22 | Closed | 250.86
PRJ-202604-0409 | 2026-04-14 | 2026-04-16 | Residential | Install - Replacement | Derek Collins | 6921.94 | 4695.5 | 4159.75 | 4159.75 | Closed | -535.75
PRJ-202604-0410 | 2026-04-22 | 2026-05-26 | Light Commercial | Tenant Improvement | Carlos Vega | 24206.78 | 17060.51 | 18178.67 | 18178.67 | Closed | 1118.16
PRJ-202604-0411 | 2026-04-18 | 2026-04-20 | Residential | Service - Major Repair | Derek Collins | 6269.51 | 3565.61 | 3406.59 | 3406.59 | Closed | -159.02
PRJ-202605-0412 | 2026-05-16 | 2026-05-18 | Residential | Service - Major Repair | Carlos Vega | 6665.86 | 4385.97 | 5261.11 | 5261.11 | Closed | 875.14
PRJ-202605-0413 | 2026-05-17 | 2026-06-01 | Light Commercial | Tenant Improvement | Brandon Shaw | 38201.06 | 30312.82 | 26251.43 | 26251.43 | Closed | -4061.39
PRJ-202605-0414 | 2026-05-14 | 2026-06-10 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 32789.52 | 24193.81 | 24996.77 | 24996.77 | Closed | 802.96
PRJ-202605-0415 | 2026-05-21 | 2026-06-20 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 47213.94 | 29966.96 | 31850.04 | 31850.04 | Closed | 1883.08
PRJ-202605-0416 | 2026-05-06 | 2026-06-16 | Light Commercial | Commercial RTU Replacement | Derek Collins | 20142.63 | 12955.51 | 12312.8 | 12312.8 | Closed | -642.71
PRJ-202605-0417 | 2026-05-16 | 2026-05-20 | Residential | Install - Replacement | Carlos Vega | 6090.1 | 4334.12 | 4562.19 | 4562.19 | Closed | 228.07
PRJ-202605-0418 | 2026-05-16 | 2026-05-18 | Residential | Service - Major Repair | Carlos Vega | 5915 | 3761.03 | 3688.75 | 3688.75 | Closed | -72.28
PRJ-202605-0419 | 2026-05-14 | 2026-05-15 | Residential | Install - New Construction | Luis Martinez | 6611.05 | 4233.42 | 3937 | 3937 | Closed | -296.42
PRJ-202605-0420 | 2026-05-19 | 2026-06-20 | Light Commercial | Tenant Improvement | Carlos Vega | 29471.37 | 22248.11 | 27316.44 | 27316.44 | Closed | 5068.33
PRJ-202605-0421 | 2026-05-01 | 2026-06-18 | Light Commercial | Commercial RTU Replacement | Derek Collins | 29957.85 | 20724.09 | 18339.91 | 18339.91 | Closed | -2384.18
PRJ-202605-0422 | 2026-05-09 | 2026-05-12 | Residential | Install - Replacement | Luis Martinez | 4850.02 | 3360.63 | 3813.49 | 3813.49 | Closed | 452.86
PRJ-202605-0423 | 2026-05-06 | 2026-07-03 | Light Commercial | Commercial RTU Replacement | Derek Collins | 41749.24 | 27360.49 | 25577.68 | 25577.68 | Closed | -1782.81
PRJ-202605-0424 | 2026-05-17 | 2026-05-19 | Residential | Service - Major Repair | Anthony Ruiz | 6373.52 | 4662.54 | 5187.21 | 5187.21 | Closed | 524.67
PRJ-202605-0425 | 2026-05-11 | 2026-07-07 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 16564.38 | 11353.34 | 10847.32 | 10847.32 | Closed | -506.02
PRJ-202605-0426 | 2026-05-13 | 2026-05-15 | Residential | Install - Replacement | Derek Collins | 3716 | 2618.19 | 2321.46 | 2321.46 | Closed | -296.73
PRJ-202605-0427 | 2026-05-16 | 2026-06-22 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 25881.1 | 17409.21 | 19192.77 | 19192.77 | Closed | 1783.56
PRJ-202605-0428 | 2026-05-25 | 2026-05-26 | Residential | Install - Replacement | Derek Collins | 4339.6 | 2984.88 | 2508.37 | 2508.37 | Closed | -476.51
PRJ-202605-0429 | 2026-05-22 | 2026-07-05 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 18917.66 | 13261.07 | 14207.3 | 14207.3 | Closed | 946.23
PRJ-202605-0430 | 2026-05-04 | 2026-05-07 | Residential | Install - Replacement | Anthony Ruiz | 7772.94 | 5021.88 | 5577.33 | 5577.33 | Closed | 555.45
PRJ-202605-0431 | 2026-05-09 | 2026-05-10 | Residential | Service - Major Repair | Derek Collins | 5810.91 | 3433.05 | 3017.86 | 3017.86 | Closed | -415.19
PRJ-202605-0432 | 2026-05-04 | 2026-05-05 | Residential | Install - Replacement | Brandon Shaw | 4568.33 | 2859.27 | 2878.58 | 2878.58 | Closed | 19.31
PRJ-202605-0433 | 2026-05-23 | 2026-05-24 | Residential | Service - Major Repair | Luis Martinez | 6806.46 | 4348.31 | 4668.13 | 4668.13 | Closed | 319.82
PRJ-202605-0434 | 2026-05-05 | 2026-06-23 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 21468.48 | 13976.17 | 15256.8 | 15256.8 | Closed | 1280.63
PRJ-202606-0435 | 2026-06-24 | 2026-06-25 | Residential | Service - Major Repair | Derek Collins | 6090.5 | 3975.8 | 3732.51 | 3732.51 | Closed | -243.29
PRJ-202606-0436 | 2026-06-22 | 2026-06-26 | Residential | Install - Replacement | Carlos Vega | 4582.19 | 2940.24 | 3099.55 | 3099.55 | Closed | 159.31
PRJ-202606-0437 | 2026-06-12 | 2026-06-16 | Residential | Install - Replacement | Luis Martinez | 6143 | 4164.66 | 3813.37 | 3813.37 | Closed | -351.29
PRJ-202606-0438 | 2026-06-07 | 2026-06-10 | Residential | Service - Major Repair | Luis Martinez | 5362.29 | 3685.81 | 4057.33 | 4057.33 | Closed | 371.52
PRJ-202606-0439 | 2026-06-16 | 2026-06-19 | Residential | Service - Major Repair | Derek Collins | 5109.78 | 3203.83 | 3007.8 | 3007.8 | Closed | -196.03
PRJ-202606-0440 | 2026-06-18 | 2026-06-20 | Residential | Install - New Construction | Anthony Ruiz | 7881.91 | 4987.02 | 5282.93 | 5282.93 | Closed | 295.91
PRJ-202606-0441 | 2026-06-06 | 2026-06-09 | Residential | Install - Replacement | Luis Martinez | 7385.57 | 4670.58 | 4360.02 | 4360.02 | Closed | -310.56
PRJ-202606-0442 | 2026-06-19 | 2026-06-20 | Residential | Install - New Construction | Brandon Shaw | 7621.47 | 4356.37 | 4282.72 | 4282.72 | Closed | -73.65
PRJ-202606-0443 | 2026-06-02 | 2026-06-06 | Residential | Install - Replacement | Anthony Ruiz | 8586.39 | 6171.72 | 7170.76 | 7170.76 | Closed | 999.04
PRJ-202606-0444 | 2026-06-08 | 2026-08-01 | Light Commercial | Tenant Improvement | Carlos Vega | 25624.69 | 15038.1 | 15126.02 | 15126.02 | Closed | 87.92
PRJ-202606-0445 | 2026-06-03 | 2026-06-06 | Residential | Service - Major Repair | Luis Martinez | 7369.59 | 4128.59 | 3509.3 | 3509.3 | Closed | -619.29
PRJ-202606-0446 | 2026-06-14 | 2026-06-18 | Residential | Install - New Construction | Brandon Shaw | 5394.37 | 3662.11 | 3171.57 | 3171.57 | Closed | -490.54
PRJ-202606-0447 | 2026-06-07 | 2026-06-10 | Residential | Install - Replacement | Carlos Vega | 6995.12 | 4773.49 | 5225.65 | 5225.65 | Closed | 452.16
PRJ-202606-0448 | 2026-06-10 | 2026-06-14 | Residential | Install - Replacement | Anthony Ruiz | 6017.58 | 3809.62 | 3680.28 | 3680.28 | Closed | -129.34
PRJ-202606-0449 | 2026-06-04 | 2026-07-04 | Light Commercial | Tenant Improvement | Derek Collins | 35333.44 | 24189.01 | 20382.55 | 20382.55 | Closed | -3806.46
PRJ-202606-0450 | 2026-06-03 | 2026-06-05 | Residential | Service - Major Repair | Carlos Vega | 4074.22 | 2802.15 | 3134.23 | 3134.23 | Closed | 332.08
PRJ-202606-0451 | 2026-06-25 | 2026-08-05 | Light Commercial | Tenant Improvement | Anthony Ruiz | 61928.18 | 44760.06 | 38046.05 | 38046.05 | Closed | -6714.01
PRJ-202606-0452 | 2026-06-19 | 2026-06-21 | Residential | Install - Replacement | Anthony Ruiz | 4927.8 | 3200.78 | 4185.3 | 4185.3 | Closed | 984.52
PRJ-202606-0453 | 2026-06-15 | 2026-07-27 | Light Commercial | Commercial Service | Carlos Vega | 13256.31 | 9819.78 | 9318.62 | 9318.62 | Closed | -501.16
PRJ-202606-0454 | 2026-06-02 | 2026-06-19 | Light Commercial | Tenant Improvement | Derek Collins | 23479.63 | 14078.77 | 16085.42 | 16085.42 | Closed | 2006.65
PRJ-202606-0455 | 2026-06-13 | 2026-06-16 | Residential | Service - Major Repair | Anthony Ruiz | 6908.37 | 3784.43 | 4017.26 | 4017.26 | Closed | 232.83
PRJ-202606-0456 | 2026-06-02 | 2026-06-20 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 44543.44 | 34657.72 | 43855.27 | 43855.27 | Closed | 9197.55
PRJ-202606-0457 | 2026-06-09 | 2026-06-10 | Residential | Install - New Construction | Derek Collins | 7133.25 | 4255.16 | 4644.82 | 4644.82 | Closed | 389.66
PRJ-202606-0458 | 2026-06-14 | 2026-06-17 | Residential | Install - New Construction | Anthony Ruiz | 6326.01 | 4098.6 | 3483.81 | 3483.81 | Closed | -614.79
PRJ-202606-0459 | 2026-06-25 | 2026-08-06 | Light Commercial | Tenant Improvement | Anthony Ruiz | 13256.31 | 9233.64 | 7848.6 | 7848.6 | Closed | -1385.04
PRJ-202606-0460 | 2026-06-22 | 2026-06-23 | Residential | Service - Major Repair | Brandon Shaw | 7127.65 | 4331.43 | 3552.59 | 3552.59 | Closed | -778.84
PRJ-202606-0461 | 2026-06-06 | 2026-06-10 | Residential | Install - Replacement | Anthony Ruiz | 4656.28 | 2770.74 | 2887.65 | 2887.65 | Closed | 116.91
PRJ-202606-0462 | 2026-06-20 | 2026-08-10 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 28169.33 | 16992.29 | 18990.21 | 18990.21 | Closed | 1997.92
PRJ-202606-0463 | 2026-06-02 | 2026-06-05 | Residential | Install - Replacement | Derek Collins | 5524.64 | 3150.09 | 2941.71 | 2941.71 | Closed | -208.38
PRJ-202606-0464 | 2026-06-17 | 2026-06-18 | Residential | Service - Major Repair | Anthony Ruiz | 8628.99 | 5853.28 | 6247.06 | 6247.06 | Closed | 393.78
PRJ-202606-0465 | 2026-06-16 | 2026-06-18 | Residential | Install - New Construction | Derek Collins | 5712.32 | 3546.87 | 3388.88 | 3388.88 | Closed | -157.99
PRJ-202607-0466 | 2026-07-14 | 2026-07-18 | Residential | Install - New Construction | Derek Collins | 7964.86 | 4744.72 | 4490.67 | 4490.67 | Closed | -254.05
PRJ-202607-0467 | 2026-07-15 | 2026-07-19 | Residential | Install - Replacement | Luis Martinez | 5540.38 | 3921.25 | 4333.28 | 4333.28 | Closed | 412.03
PRJ-202607-0468 | 2026-07-02 | 2026-07-05 | Residential | Service - Major Repair | Derek Collins | 4723.61 | 3240.37 | 2951.66 | 2951.66 | Closed | -288.71
PRJ-202607-0469 | 2026-07-25 | 2026-07-28 | Residential | Install - Replacement | Carlos Vega | 3711.77 | 2589.75 | 2832.71 | 2832.71 | Closed | 242.96
PRJ-202607-0470 | 2026-07-13 | 2026-09-09 | Light Commercial | Tenant Improvement | Derek Collins | 13256.31 | 8602.96 | 8566 | 8566 | Closed | -36.96
PRJ-202607-0471 | 2026-07-16 | 2026-07-20 | Residential | Service - Major Repair | Carlos Vega | 4740.95 | 2483.78 | 2126.68 | 2126.68 | Closed | -357.1
PRJ-202607-0472 | 2026-07-22 | 2026-07-25 | Residential | Service - Major Repair | Derek Collins | 8652.55 | 5522.79 | 4638.44 | 4638.44 | Closed | -884.35
PRJ-202607-0473 | 2026-07-20 | 2026-07-24 | Residential | Service - Major Repair | Anthony Ruiz | 6356.8 | 4347.54 | 5039.18 | 5039.18 | Closed | 691.64
PRJ-202607-0474 | 2026-07-01 | 2026-07-05 | Residential | Service - Major Repair | Carlos Vega | 4261.05 | 2650.54 | 2849.32 | 2849.32 | Closed | 198.78
PRJ-202607-0475 | 2026-07-08 | 2026-07-11 | Residential | Service - Major Repair | Brandon Shaw | 3915.3 | 2472.72 | 2460.53 | 2460.53 | Closed | -12.19
PRJ-202607-0476 | 2026-07-15 | 2026-07-18 | Residential | Install - Replacement | Carlos Vega | 4621.7 | 2869.41 | 2439 | 2439 | Closed | -430.41
PRJ-202607-0477 | 2026-07-06 | 2026-08-15 | Light Commercial | Tenant Improvement | Luis Martinez | 39501.37 | 28777.95 | 29462.48 | 29462.48 | Closed | 684.53
PRJ-202607-0478 | 2026-07-07 | 2026-08-20 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 48207.13 | 35265.13 | 37968.58 | 37968.58 | Closed | 2703.45
PRJ-202607-0479 | 2026-07-06 | 2026-07-30 | Light Commercial | Commercial Service | Luis Martinez | 29537.55 | 20745.99 | 22626.72 | 22626.72 | Closed | 1880.73
PRJ-202607-0480 | 2026-07-06 | 2026-07-07 | Residential | Install - Replacement | Carlos Vega | 5114.99 | 3153.59 | 3457.94 | 3457.94 | Closed | 304.35
PRJ-202607-0481 | 2026-07-14 | 2026-07-15 | Residential | Install - Replacement | Luis Martinez | 8779.64 | 5076.4 | 5574.49 | 5574.49 | Closed | 498.09
PRJ-202607-0482 | 2026-07-11 | 2026-07-13 | Residential | Install - Replacement | Luis Martinez | 3711.77 | 2308.29 | 2227.64 | 2227.64 | Closed | -80.65
PRJ-202607-0483 | 2026-07-06 | 2026-07-08 | Residential | Install - Replacement | Derek Collins | 5256.71 | 3673.32 | 3410.09 | 3410.09 | Closed | -263.23
PRJ-202607-0484 | 2026-07-24 | 2026-09-08 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 43939.9 | 33029 | 41758.44 | 41758.44 | Closed | 8729.44
PRJ-202607-0485 | 2026-07-21 | 2026-07-24 | Residential | Install - New Construction | Luis Martinez | 6098.76 | 3939.53 | 4262.92 | 4262.92 | Closed | 323.39
PRJ-202607-0486 | 2026-07-24 | 2026-07-27 | Residential | Install - Replacement | Anthony Ruiz | 6665.88 | 3774.57 | 3886.9 | 3886.9 | Closed | 112.33
PRJ-202607-0487 | 2026-07-12 | 2026-07-31 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 33017.15 | 24391.88 | 22355.79 | 22355.79 | Closed | -2036.09
PRJ-202607-0488 | 2026-07-06 | 2026-07-08 | Residential | Install - Replacement | Derek Collins | 5252.93 | 3189.55 | 3208.97 | 3208.97 | Closed | 19.42
PRJ-202607-0489 | 2026-07-19 | 2026-07-23 | Residential | Install - Replacement | Brandon Shaw | 7900.35 | 4988.16 | 5257.86 | 5257.86 | Closed | 269.7
PRJ-202607-0490 | 2026-07-19 | 2026-07-23 | Residential | Service - Major Repair | Carlos Vega | 7445.95 | 4706.06 | 5289.68 | 5289.68 | Closed | 583.62
PRJ-202607-0491 | 2026-07-01 | 2026-07-05 | Residential | Install - Replacement | Brandon Shaw | 7199.27 | 4527.83 | 4211.81 | 4211.81 | Closed | -316.02
PRJ-202607-0492 | 2026-07-04 | 2026-07-07 | Residential | Install - Replacement | Carlos Vega | 7436.3 | 5192.04 | 5958.54 | 5958.54 | Closed | 766.5
PRJ-202607-0493 | 2026-07-14 | 2026-08-27 | Light Commercial | Tenant Improvement | Brandon Shaw | 45996.61 | 27104.48 | 27339.39 | 27339.39 | Closed | 234.91
PRJ-202607-0494 | 2026-07-22 | 2026-09-04 | Light Commercial | Tenant Improvement | Carlos Vega | 38492.67 | 24608.16 | 28739.66 | 28739.66 | Closed | 4131.5
PRJ-202607-0495 | 2026-07-13 | 2026-08-22 | Light Commercial | Commercial Service | Brandon Shaw | 34191.16 | 24308.53 | 24583.18 | 24583.18 | Closed | 274.65
PRJ-202608-0496 | 2026-08-18 | 2026-10-05 | Light Commercial | Commercial Service | Luis Martinez | 32870.31 | 21892.93 | 24539.39 | 24539.39 | Closed | 2646.46
PRJ-202608-0497 | 2026-08-12 | 2026-08-14 | Residential | Install - Replacement | Derek Collins | 3900.53 | 2789.39 | 2555.07 | 2555.07 | Closed | -234.32
PRJ-202608-0498 | 2026-08-05 | 2026-08-07 | Residential | Install - Replacement | Derek Collins | 4021.19 | 2697.27 | 2716.07 | 2716.07 | Closed | 18.8
PRJ-202608-0499 | 2026-08-16 | 2026-08-19 | Residential | Install - New Construction | Carlos Vega | 4044.96 | 2926.93 | 2545.11 | 2545.11 | Closed | -381.82
PRJ-202608-0500 | 2026-08-11 | 2026-09-19 | Light Commercial | Commercial Service | Carlos Vega | 18027.23 | 13017.29 | 13292.5 | 13292.5 | Closed | 275.21
PRJ-202608-0501 | 2026-08-20 | 2026-08-22 | Residential | Service - Major Repair | Brandon Shaw | 6758.21 | 4230.46 | 4292.7 | 4292.7 | Closed | 62.24
PRJ-202608-0502 | 2026-08-24 | 2026-10-02 | Light Commercial | Tenant Improvement | Carlos Vega | 21187.67 | 14417.82 | 15683.16 | 15683.16 | Closed | 1265.34
PRJ-202608-0503 | 2026-08-11 | 2026-08-28 | Light Commercial | Commercial Service | Luis Martinez | 49165.87 | 38989.67 | 42488.5 | 42488.5 | Closed | 3498.83
PRJ-202608-0504 | 2026-08-05 | 2026-08-06 | Residential | Service - Major Repair | Derek Collins | 5089.06 | 3646.32 | 3449.23 | 3449.23 | Closed | -197.09
PRJ-202608-0505 | 2026-08-19 | 2026-09-09 | Light Commercial | Tenant Improvement | Carlos Vega | 41431.58 | 28204.59 | 29643.41 | 29643.41 | Closed | 1438.82
PRJ-202608-0506 | 2026-08-08 | 2026-10-02 | Light Commercial | Commercial Service | Derek Collins | 13256.31 | 9055.42 | 9455.03 | 9455.03 | Closed | 399.61
PRJ-202608-0507 | 2026-08-09 | 2026-08-12 | Residential | Install - Replacement | Derek Collins | 7876.8 | 4352.8 | 4270.94 | 4270.94 | Closed | -81.86
PRJ-202608-0508 | 2026-08-06 | 2026-08-07 | Residential | Install - Replacement | Luis Martinez | 6095.03 | 3978.9 | 4541.74 | 4541.74 | Closed | 562.84
PRJ-202608-0509 | 2026-08-05 | 2026-08-06 | Residential | Service - Major Repair | Derek Collins | 5626.98 | 3388.22 | 3083.37 | 3083.37 | Closed | -304.85
PRJ-202608-0510 | 2026-08-17 | 2026-08-20 | Residential | Install - Replacement | Anthony Ruiz | 6918.06 | 4586.76 | 5933.59 | 5933.59 | Closed | 1346.83
PRJ-202608-0511 | 2026-08-03 | 2026-08-05 | Residential | Install - New Construction | Derek Collins | 6232.8 | 4118.17 | 4239.1 | 4239.1 | Closed | 120.93
PRJ-202608-0512 | 2026-08-03 | 2026-08-18 | Light Commercial | Commercial Service | Brandon Shaw | 36891.98 | 25712.36 | 24605.53 | 24605.53 | Closed | -1106.83
PRJ-202608-0513 | 2026-08-23 | 2026-09-20 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 31533.74 | 21755.18 | 21730.96 | 21730.96 | Closed | -24.22
PRJ-202608-0514 | 2026-08-06 | 2026-09-05 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 51644.38 | 33620.89 | 39079.17 | 39079.17 | Closed | 5458.28
PRJ-202608-0515 | 2026-08-24 | 2026-08-25 | Residential | Service - Major Repair | Brandon Shaw | 5410.06 | 3480.33 | 3228.48 | 3228.48 | Closed | -251.85
PRJ-202608-0516 | 2026-08-03 | 2026-08-05 | Residential | Install - Replacement | Derek Collins | 7690.29 | 4922.45 | 4585.5 | 4585.5 | Closed | -336.95
PRJ-202608-0517 | 2026-08-15 | 2026-10-03 | Light Commercial | Tenant Improvement | Brandon Shaw | 40991.24 | 32486.75 | 27409.54 | 27409.54 | Closed | -5077.21
PRJ-202608-0518 | 2026-08-08 | 2026-08-12 | Residential | Install - Replacement | Brandon Shaw | 5422.82 | 3889.1 | 3138.76 | 3138.76 | Closed | -750.34
PRJ-202608-0519 | 2026-08-19 | 2026-08-23 | Residential | Install - Replacement | Carlos Vega | 8477.65 | 5950.71 | 5695.01 | 5695.01 | Closed | -255.7
PRJ-202608-0520 | 2026-08-03 | 2026-08-07 | Residential | Install - Replacement | Brandon Shaw | 7155.14 | 4093.29 | 3824.27 | 3824.27 | Closed | -269.02
PRJ-202608-0521 | 2026-08-09 | 2026-08-12 | Residential | Install - Replacement | Luis Martinez | 5348.81 | 3921.06 | 3601.84 | 3601.84 | Closed | -319.22
PRJ-202608-0522 | 2026-08-15 | 2026-08-18 | Residential | Install - Replacement | Anthony Ruiz | 5459.56 | 3628.98 | 4371.81 | 4371.81 | Closed | 742.83
PRJ-202608-0523 | 2026-08-24 | 2026-08-27 | Residential | Install - Replacement | Anthony Ruiz | 7265.96 | 4338.2 | 4479.23 | 4479.23 | Closed | 141.03
PRJ-202608-0524 | 2026-08-13 | 2026-08-14 | Residential | Service - Major Repair | Carlos Vega | 5823.42 | 3403.76 | 3255.1 | 3255.1 | Closed | -148.66
PRJ-202608-0525 | 2026-08-08 | 2026-08-11 | Residential | Install - Replacement | Anthony Ruiz | 5317.8 | 3805.98 | 3962.66 | 3962.66 | Closed | 156.68
PRJ-202608-0526 | 2026-08-18 | 2026-08-19 | Residential | Install - New Construction | Brandon Shaw | 7054.99 | 4858.29 | 5347.38 | 5347.38 | Closed | 489.09
PRJ-202608-0527 | 2026-08-06 | 2026-08-09 | Residential | Service - Major Repair | Anthony Ruiz | 7018.31 | 4670.59 | 4971.73 | 4971.73 | Closed | 301.14
PRJ-202608-0528 | 2026-08-11 | 2026-08-13 | Residential | Install - New Construction | Derek Collins | 7175.2 | 4620.95 | 4434.89 | 4434.89 | Closed | -186.06
PRJ-202608-0529 | 2026-08-20 | 2026-08-21 | Residential | Install - Replacement | Brandon Shaw | 6682.18 | 4389.08 | 3835.04 | 3835.04 | Closed | -554.04
PRJ-202608-0530 | 2026-08-19 | 2026-08-20 | Residential | Install - Replacement | Derek Collins | 5685.72 | 3870.42 | 3718.81 | 3718.81 | Closed | -151.61
PRJ-202608-0531 | 2026-08-19 | 2026-08-22 | Residential | Install - Replacement | Brandon Shaw | 3711.77 | 2559.81 | 2133.04 | 2133.04 | Closed | -426.77
PRJ-202609-0532 | 2026-09-03 | 2026-09-07 | Residential | Install - Replacement | Luis Martinez | 5401.56 | 3640.23 | 4097.53 | 4097.53 | Closed | 457.3
PRJ-202609-0533 | 2026-09-17 | 2026-09-20 | Residential | Install - Replacement | Luis Martinez | 5198.03 | 3492.76 | 3341.74 | 3341.74 | Closed | -151.02
PRJ-202609-0534 | 2026-09-22 | 2026-09-25 | Residential | Install - New Construction | Luis Martinez | 4998.03 | 3219.46 | 3096.97 | 3096.97 | Closed | -122.49
PRJ-202609-0535 | 2026-09-20 | 2026-09-23 | Residential | Service - Major Repair | Derek Collins | 7023.03 | 3895.23 | 4026.35 | 4026.35 | Closed | 131.12
PRJ-202609-0536 | 2026-09-09 | 2026-09-12 | Residential | Install - New Construction | Anthony Ruiz | 6687.48 | 4347.34 | 4528.26 | 4528.26 | Closed | 180.92
PRJ-202609-0537 | 2026-09-18 | 2026-09-22 | Residential | Install - Replacement | Derek Collins | 7418.26 | 4703.49 | 4062 | 4062 | Closed | -641.49
PRJ-202609-0538 | 2026-09-09 | 2026-09-12 | Residential | Install - New Construction | Brandon Shaw | 3711.77 | 2214.11 | 2173.97 | 2173.97 | Closed | -40.14
PRJ-202609-0539 | 2026-09-17 | 2026-11-07 | Light Commercial | Tenant Improvement | Derek Collins | 35761.92 | 26418.23 | 27406.98 | 27406.98 | Closed | 988.75
PRJ-202609-0540 | 2026-09-04 | 2026-09-08 | Residential | Service - Major Repair | Anthony Ruiz | 8218.79 | 5333.08 | 5739.01 | 5739.01 | Closed | 405.93
PRJ-202609-0541 | 2026-09-24 | 2026-09-28 | Residential | Install - Replacement | Luis Martinez | 6064.49 | 3906.53 | 4336.1 | 4336.1 | Closed | 429.57
PRJ-202609-0542 | 2026-09-01 | 2026-09-04 | Residential | Install - Replacement | Anthony Ruiz | 3711.77 | 2328.2 | 2950.63 | 2950.63 | Closed | 622.43
PRJ-202609-0543 | 2026-09-13 | 2026-09-14 | Residential | Install - Replacement | Brandon Shaw | 6816.32 | 4449.65 | 5030.21 | 5030.21 | Closed | 580.56
PRJ-202609-0544 | 2026-09-03 | 2026-09-05 | Residential | Service - Major Repair | Anthony Ruiz | 6101.17 | 4162.78 | 5591.23 | 5591.23 | Closed | 1428.45
PRJ-202609-0545 | 2026-09-16 | 2026-10-15 | Light Commercial | Commercial Service | Carlos Vega | 29979.29 | 18727.66 | 18294.66 | 18294.66 | Closed | -433
PRJ-202609-0546 | 2026-09-12 | 2026-09-15 | Residential | Install - New Construction | Carlos Vega | 4704.39 | 3007.83 | 2592.1 | 2592.1 | Closed | -415.73
PRJ-202609-0547 | 2026-09-11 | 2026-09-15 | Residential | Install - Replacement | Brandon Shaw | 4642.2 | 3070.84 | 2632.79 | 2632.79 | Closed | -438.05
PRJ-202609-0548 | 2026-09-15 | 2026-09-18 | Residential | Install - New Construction | Brandon Shaw | 4241.03 | 2759.22 | 2466.08 | 2466.08 | Closed | -293.14
PRJ-202609-0549 | 2026-09-08 | 2026-09-10 | Residential | Install - Replacement | Luis Martinez | 5649.62 | 3743.57 | 4538.59 | 4538.59 | Closed | 795.02
PRJ-202609-0550 | 2026-09-18 | 2026-11-05 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 40474.45 | 23508.09 | 19981.88 | 19981.88 | Closed | -3526.21
PRJ-202609-0551 | 2026-09-15 | 2026-09-16 | Residential | Install - Replacement | Carlos Vega | 6429.46 | 4271.98 | 3723.36 | 3723.36 | Closed | -548.62
PRJ-202609-0552 | 2026-09-02 | 2026-09-03 | Residential | Install - Replacement | Luis Martinez | 5677.27 | 3944.65 | 3771.95 | 3771.95 | Closed | -172.7
PRJ-202609-0553 | 2026-09-25 | 2026-09-26 | Residential | Install - Replacement | Anthony Ruiz | 6736.96 | 3813.43 | 3679.85 | 3679.85 | Closed | -133.58
PRJ-202609-0554 | 2026-09-09 | 2026-09-10 | Residential | Service - Major Repair | Luis Martinez | 5229.3 | 2850.55 | 3416.39 | 3416.39 | Closed | 565.84
PRJ-202609-0555 | 2026-09-08 | 2026-09-10 | Residential | Install - Replacement | Luis Martinez | 8149.26 | 4807.36 | 4974.95 | 4974.95 | Closed | 167.59
PRJ-202609-0556 | 2026-09-06 | 2026-10-10 | Light Commercial | Tenant Improvement | Anthony Ruiz | 29444.69 | 20626 | 21340.32 | 21340.32 | Closed | 714.32
PRJ-202609-0557 | 2026-09-23 | 2026-09-27 | Residential | Install - Replacement | Luis Martinez | 7203.43 | 4560.09 | 5185.98 | 5185.98 | Closed | 625.89
PRJ-202609-0558 | 2026-09-21 | 2026-09-24 | Residential | Install - Replacement | Derek Collins | 6543.11 | 3717.8 | 3747.84 | 3747.84 | Closed | 30.04
PRJ-202609-0559 | 2026-09-09 | 2026-09-12 | Residential | Install - Replacement | Carlos Vega | 4434.89 | 3229.19 | 3106.26 | 3106.26 | Closed | -122.93
PRJ-202609-0560 | 2026-09-08 | 2026-09-09 | Residential | Install - Replacement | Luis Martinez | 5592.73 | 3585.4 | 4403.01 | 4403.01 | Closed | 817.61
PRJ-202610-0561 | 2026-10-21 | 2026-10-23 | Residential | Install - Replacement | Brandon Shaw | 6837.08 | 4657.32 | 4949.65 | 4949.65 | Closed | 292.33
PRJ-202610-0562 | 2026-10-01 | 2026-10-03 | Residential | Install - New Construction | Anthony Ruiz | 5495.97 | 3573.82 | 4426.81 | 4426.81 | Closed | 852.99
PRJ-202610-0563 | 2026-10-13 | 2026-11-29 | Light Commercial | Tenant Improvement | Luis Martinez | 40068.57 | 26396.35 | 28342.59 | 28342.59 | Active | 1946.24
PRJ-202610-0564 | 2026-10-15 | 2026-10-17 | Residential | Install - Replacement | Derek Collins | 6945.94 | 3472.97 | 3165.59 | 3165.59 | Closed | -307.38
PRJ-202610-0565 | 2026-10-01 | 2026-10-05 | Residential | Install - Replacement | Carlos Vega | 6115.21 | 3694.57 | 3457.4 | 3457.4 | Closed | -237.17
PRJ-202610-0566 | 2026-10-14 | 2026-10-17 | Residential | Install - Replacement | Anthony Ruiz | 7322.1 | 4602.66 | 5223.49 | 5223.49 | Closed | 620.83
PRJ-202610-0567 | 2026-10-01 | 2026-10-04 | Residential | Install - Replacement | Carlos Vega | 5843.25 | 4014.22 | 3900.28 | 3900.28 | Closed | -113.94
PRJ-202610-0568 | 2026-10-20 | 2026-10-23 | Residential | Install - Replacement | Luis Martinez | 8705.33 | 5773.54 | 6076.82 | 6076.82 | Closed | 303.28
PRJ-202610-0569 | 2026-10-22 | 2026-10-24 | Residential | Service - Major Repair | Luis Martinez | 7989.13 | 5048.8 | 5346.39 | 5346.39 | Closed | 297.59
PRJ-202610-0570 | 2026-10-15 | 2026-10-17 | Residential | Install - Replacement | Anthony Ruiz | 5948.56 | 4385.21 | 4704.35 | 4704.35 | Closed | 319.14
PRJ-202610-0571 | 2026-10-06 | 2026-10-09 | Residential | Install - Replacement | Carlos Vega | 6421.51 | 4411.33 | 4177.78 | 4177.78 | Closed | -233.55
PRJ-202610-0572 | 2026-10-12 | 2026-10-16 | Residential | Install - Replacement | Carlos Vega | 8071.25 | 5909.08 | 6003.42 | 6003.42 | Closed | 94.34
PRJ-202610-0573 | 2026-10-06 | 2026-11-18 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 28777.1 | 20142.41 | 20855.67 | 20855.67 | Active | 713.26
PRJ-202610-0574 | 2026-10-21 | 2026-10-24 | Residential | Install - Replacement | Carlos Vega | 6893.32 | 4157.75 | 4248.71 | 4248.71 | Closed | 90.96
PRJ-202610-0575 | 2026-10-06 | 2026-10-09 | Residential | Install - Replacement | Luis Martinez | 7136.89 | 4318.74 | 4847.42 | 4847.42 | Closed | 528.68
PRJ-202610-0576 | 2026-10-08 | 2026-10-11 | Residential | Install - Replacement | Derek Collins | 7947.95 | 4804.08 | 5241.04 | 5241.04 | Closed | 436.96
PRJ-202610-0577 | 2026-10-03 | 2026-10-26 | Light Commercial | Commercial RTU Replacement | Derek Collins | 30736.53 | 23967.58 | 21440.39 | 21440.39 | Closed | -2527.19
PRJ-202610-0578 | 2026-10-21 | 2026-10-25 | Residential | Install - Replacement | Anthony Ruiz | 4858.29 | 2884.26 | 2871.62 | 2871.62 | Closed | -12.64
PRJ-202610-0579 | 2026-10-05 | 2026-10-09 | Residential | Install - Replacement | Brandon Shaw | 5727.6 | 3757.45 | 4080.02 | 4080.02 | Closed | 322.57
PRJ-202610-0580 | 2026-10-03 | 2026-11-29 | Light Commercial | Tenant Improvement | Anthony Ruiz | 38638.59 | 29574.75 | 32648.34 | 32648.34 | Active | 3073.59
PRJ-202610-0581 | 2026-10-17 | 2026-10-18 | Residential | Install - Replacement | Derek Collins | 7414.94 | 4138.39 | 4302.85 | 4302.85 | Closed | 164.46
PRJ-202610-0582 | 2026-10-08 | 2026-10-10 | Residential | Install - Replacement | Derek Collins | 5780.23 | 3558.46 | 3703.54 | 3703.54 | Closed | 145.08
PRJ-202611-0583 | 2026-11-15 | 2026-11-17 | Residential | Install - Replacement | Carlos Vega | 5258.79 | 3709.11 | 4314.05 | 4314.05 | Active | 604.94
PRJ-202611-0584 | 2026-11-11 | 2026-11-12 | Residential | Service - Major Repair | Brandon Shaw | 4829.55 | 3546.46 | 3699.44 | 3699.44 | Closed | 152.98
PRJ-202611-0585 | 2026-11-13 | 2026-11-15 | Residential | Install - Replacement | Derek Collins | 6321.98 | 3696.95 | 3351.4 | 3351.4 | Closed | -345.55
PRJ-202611-0586 | 2026-11-16 | 2026-11-20 | Residential | Service - Major Repair | Derek Collins | 6741.36 | 4293.83 | 3993.87 | 3993.87 | Active | -299.96
PRJ-202611-0587 | 2026-11-07 | 2026-11-09 | Residential | Service - Major Repair | Luis Martinez | 7317.66 | 4579.73 | 4729.22 | 4729.22 | Closed | 149.49
PRJ-202611-0588 | 2026-11-24 | 2026-11-26 | Residential | Install - New Construction | Derek Collins | 5357.8 | 3321.98 | 2864.64 | 2864.64 | Active | -457.34
PRJ-202611-0589 | 2026-11-01 | 2026-12-16 | Light Commercial | Tenant Improvement | Carlos Vega | 25279.53 | 16706.89 | 14473.83 | 14473.83 | Active | -2233.06
PRJ-202611-0590 | 2026-11-12 | 2026-11-15 | Residential | Service - Major Repair | Derek Collins | 8049.26 | 5255.6 | 5363.66 | 5363.66 | Closed | 108.06
PRJ-202611-0591 | 2026-11-25 | 2026-11-28 | Residential | Install - Replacement | Anthony Ruiz | 4692.62 | 2594.64 | 2908.21 | 2908.21 | Active | 313.57
PRJ-202611-0592 | 2026-11-15 | 2026-11-19 | Residential | Install - Replacement | Luis Martinez | 7808.61 | 5123.28 | 5131.16 | 5131.16 | Active | 7.88
PRJ-202611-0593 | 2026-11-21 | 2026-11-25 | Residential | Install - New Construction | Luis Martinez | 6366.79 | 4085.34 | 3997.48 | 3997.48 | Active | -87.86
PRJ-202611-0594 | 2026-11-10 | 2026-11-11 | Residential | Install - New Construction | Derek Collins | 4856.07 | 3409.26 | 3509.17 | 3509.17 | Closed | 99.91
PRJ-202611-0595 | 2026-11-23 | 2026-11-25 | Residential | Install - Replacement | Derek Collins | 6836.72 | 3507.15 | 3791.65 | 3791.65 | Active | 284.5
PRJ-202611-0596 | 2026-11-15 | 2026-12-24 | Light Commercial | Commercial Service | Anthony Ruiz | 37240 | 26725.55 | 32756.91 | 32756.91 | Active | 6031.36
PRJ-202611-0597 | 2026-11-02 | 2026-11-06 | Residential | Service - Major Repair | Brandon Shaw | 6012.93 | 3676.24 | 4090.68 | 4090.68 | Closed | 414.44
PRJ-202611-0598 | 2026-11-24 | 2027-01-11 | Light Commercial | Commercial Service | Brandon Shaw | 21624.41 | 17140.9 | 7401.14 | 15973.08 | Active | -1167.82
PRJ-202611-0599 | 2026-11-24 | 2026-12-08 | Light Commercial | Commercial Service | Derek Collins | 38436.12 | 24270.88 | 21926.03 | 21926.03 | Active | -2344.85
PRJ-202611-0600 | 2026-11-11 | 2027-01-01 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 41524.62 | 28391.15 | 6247.11 | 24988.45 | Active | -3402.7
PRJ-202611-0601 | 2026-11-22 | 2026-11-25 | Residential | Install - Replacement | Anthony Ruiz | 6490.56 | 4046.79 | 4627.58 | 4627.58 | Active | 580.79
PRJ-202611-0602 | 2026-11-25 | 2026-11-27 | Residential | Service - Major Repair | Derek Collins | 6913.45 | 4473.5 | 4154.32 | 4154.32 | Active | -319.18
PRJ-202611-0603 | 2026-11-04 | 2026-11-07 | Residential | Install - Replacement | Brandon Shaw | 6946.04 | 4580.37 | 4728.42 | 4728.42 | Closed | 148.05
PRJ-202611-0604 | 2026-11-05 | 2026-11-06 | Residential | Service - Major Repair | Luis Martinez | 7211.65 | 3773.1 | 4675.52 | 4675.52 | Closed | 902.42
PRJ-202611-0605 | 2026-11-09 | 2026-11-23 | Light Commercial | Commercial RTU Replacement | Anthony Ruiz | 40932.89 | 30195.18 | 34496.78 | 34496.78 | Active | 4301.6
PRJ-202611-0606 | 2026-11-23 | 2026-11-27 | Residential | Service - Major Repair | Derek Collins | 5352.62 | 3569.99 | 3442.27 | 3442.27 | Active | -127.72
PRJ-202611-0607 | 2026-11-19 | 2026-12-12 | Light Commercial | Commercial Service | Brandon Shaw | 38679.82 | 29738.07 | 25827.31 | 25827.31 | Active | -3910.76
PRJ-202611-0608 | 2026-11-17 | 2027-01-05 | Light Commercial | Commercial Service | Brandon Shaw | 35077.46 | 21644.45 | 5275.67 | 21102.7 | Active | -541.75
PRJ-202611-0609 | 2026-11-08 | 2026-12-06 | Light Commercial | Tenant Improvement | Luis Martinez | 42823.95 | 28951.91 | 30231.38 | 30231.38 | Active | 1279.47
PRJ-202611-0610 | 2026-11-23 | 2026-11-26 | Residential | Install - Replacement | Luis Martinez | 5374.11 | 3390.3 | 3412.39 | 3412.39 | Active | 22.09
PRJ-202611-0611 | 2026-11-01 | 2026-11-05 | Residential | Install - Replacement | Anthony Ruiz | 8958.56 | 6104.34 | 5949.45 | 5949.45 | Closed | -154.89
PRJ-202611-0612 | 2026-11-18 | 2026-11-19 | Residential | Install - Replacement | Carlos Vega | 6322.26 | 3925.11 | 4612 | 4612 | Active | 686.89
PRJ-202612-0613 | 2026-12-02 | 2026-12-03 | Residential | Install - Replacement | Carlos Vega | 7528.82 | 5251.96 | 5728.23 | 5728.23 | Active | 476.27
PRJ-202612-0614 | 2026-12-16 | 2026-12-17 | Residential | Install - Replacement | Derek Collins | 9088.72 | 5985.55 | 6903.68 | 6903.68 | Active | 918.13
PRJ-202612-0615 | 2026-12-03 | 2026-12-25 | Light Commercial | Commercial RTU Replacement | Carlos Vega | 31650.67 | 24364.4 | 24464.28 | 24464.28 | Active | 99.88
PRJ-202612-0616 | 2026-12-13 | 2026-12-15 | Residential | Service - Major Repair | Anthony Ruiz | 5380.98 | 3415.55 | 3502.76 | 3502.76 | Active | 87.21
PRJ-202612-0617 | 2026-12-24 | 2026-12-26 | Residential | Service - Major Repair | Carlos Vega | 6344.19 | 4165 | 3957.69 | 3957.69 | Active | -207.31
PRJ-202612-0618 | 2026-12-22 | 2027-01-11 | Light Commercial | Tenant Improvement | Anthony Ruiz | 40004.05 | 27728.2 | 18735.83 | 28960.59 | Active | 1232.39
PRJ-202612-0619 | 2026-12-22 | 2026-12-24 | Residential | Install - New Construction | Carlos Vega | 7333.3 | 4634.8 | 4538.7 | 4538.7 | Active | -96.1
PRJ-202612-0620 | 2026-12-09 | 2026-12-12 | Residential | Service - Major Repair | Luis Martinez | 10063.75 | 6968.73 | 7347.96 | 7347.96 | Active | 379.23
PRJ-202612-0621 | 2026-12-08 | 2026-12-11 | Residential | Install - Replacement | Anthony Ruiz | 7751.25 | 5540.26 | 5403.59 | 5403.59 | Active | -136.67
PRJ-202612-0622 | 2026-12-16 | 2027-02-04 | Light Commercial | Commercial Service | Luis Martinez | 37553.5 | 25419.92 | 7304.71 | 29218.84 | Active | 3798.92
PRJ-202612-0623 | 2026-12-12 | 2026-12-14 | Residential | Service - Major Repair | Derek Collins | 4324.34 | 2552.5 | 2436.84 | 2436.84 | Active | -115.66
PRJ-202612-0624 | 2026-12-13 | 2026-12-16 | Residential | Install - Replacement | Derek Collins | 6481.18 | 4127.49 | 4141.73 | 4141.73 | Active | 14.24
PRJ-202612-0625 | 2026-12-03 | 2026-12-05 | Residential | Install - Replacement | Anthony Ruiz | 3711.77 | 2472.82 | 2647.58 | 2647.58 | Active | 174.76
PRJ-202612-0626 | 2026-12-25 | 2026-12-27 | Residential | Service - Major Repair | Anthony Ruiz | 6165.71 | 3676.77 | 4041.27 | 4041.27 | Active | 364.5
PRJ-202612-0627 | 2026-12-13 | 2026-12-15 | Residential | Install - Replacement | Derek Collins | 5816.83 | 3702.97 | 3439.34 | 3439.34 | Active | -263.63
PRJ-202612-0628 | 2026-12-13 | 2026-12-15 | Residential | Install - Replacement | Anthony Ruiz | 5289.57 | 3826.51 | 4597.08 | 4597.08 | Active | 770.57
PRJ-202612-0629 | 2026-12-23 | 2027-01-30 | Light Commercial | Commercial RTU Replacement | Brandon Shaw | 33685.67 | 21460.65 | 16568.77 | 23437.75 | Active | 1977.1
PRJ-202612-0630 | 2026-12-06 | 2026-12-21 | Light Commercial | Commercial RTU Replacement | Luis Martinez | 26902.47 | 18747.98 | 18453.61 | 18453.61 | Active | -294.37
PRJ-202612-0631 | 2026-12-25 | 2026-12-28 | Residential | Install - New Construction | Derek Collins | 6651.38 | 4458.47 | 4202.79 | 4202.79 | Active | -255.68
PRJ-202612-0632 | 2026-12-13 | 2026-12-14 | Residential | Install - New Construction | Anthony Ruiz | 4773.32 | 3271.29 | 3179.29 | 3179.29 | Active | -92
PRJ-202612-0633 | 2026-12-13 | 2026-12-17 | Residential | Install - New Construction | Derek Collins | 6183.04 | 3485.18 | 3620.53 | 3620.53 | Active | 135.35
PRJ-202612-0634 | 2026-12-22 | 2027-02-08 | Light Commercial | Tenant Improvement | Brandon Shaw | 13256.31 | 8160.8 | 4771.72 | 8969.41 | Active | 808.61

## Starting Point
PM

## Completed Solution
PM | Active Projects | Projects Over Budget | % Over Budget
Anthony Ruiz | 12 | 10 | 83.33% | Anyone can move projects forward. The real question is: how many are actually finishing within the budget you approved? Projects Exceeding Budget % forces accountability and reveals whether your operation is disciplined or reactive.
Luis Martinez | 8 | 6 | 75%
Carlos Vega | 9 | 5 | 55.56%
Brandon Shaw | 5 | 2 | 40%
Derek Collins | 12 | 4 | 33.33%
If you'd like help implementing these KPIs or getting insights like this for your company, email me at questions@databoards.io.