## Dashboard
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
EXECUTIVE PROJECT DASHBOARD
High-level overview of milestone progression, task statuses, critical path risks, and project health.
Project Name | Customer Portal Launch | Manager | Alex Morgan, PMP | Start Date | 2026-10-05 | Target End | 2027-01-15 | Reporting Date | 2026-11-10 | Project Health | At Risk
TOTAL TASKS |  | COMPLETED TASKS |  | IN PROGRESS |  | NOT STARTED |  |  | PROJECT HEALTH & GOVERNANCE EVALUATION
18 |  | 5 |  | 3 |  | 9 |  |  | PROJECT STATUS: AT RISK Overdue tasks: 1 Blocked tasks: 1 Overall completion: 37.8% Elapsed schedule: 35.3% Review the action list and Task List warnings before updating the plan.
Active scope records |  | Fully delivered items |  | Active sprint tasks |  | Backlog & future phases
OVERDUE TASKS |  | BLOCKED TASKS |  | OVERALL COMPLETION |  | DAYS REMAINING
1 |  | 1 |  | 37.78% |  | 66
Past deadline & incomplete |  | Requires escalation |  | Scope progress average |  | Calendar days to target end
PROJECT ANALYTICS & VISUAL METRICS
TOP OVERDUE & BLOCKED TASKS (ACTION REQUIRED)
Task ID | Phase | Task Name | Owner | End Date | Status | Priority | Schedule Alert | Root Cause / Escalation Note
TSK-05 | Planning | Content Taxonomy & Helpdesk Schema | Elena Rostova | 2026-11-04 | In Progress | High | Overdue | Delayed review by legal; overdue relative to reporting date.
TSK-12 | Build | Billing & Payment Gateway API | David Kim | 2026-12-18 | Blocked | Critical | Blocked | BLOCKED: Awaiting corporate merchant account verification.
UPCOMING KEY MILESTONES (NEXT FOUR TARGETS)
Milestone ID | Milestone Name | Phase | Target Date | Owner | Status | Completion % | Days Remaining
M-01 | Client Prototype Review & Approval | Design | 2026-11-20 | Alex Morgan | Not Started | 0% | 10
M-02 | Core Feature Integration Complete | Build | 2026-12-18 | Marcus Vance | Not Started | 0% | 38
M-03 | UAT & Beta User Sign-Off | Testing | 2027-01-06 | Alex Morgan | Not Started | 0% | 57
M-04 | Production Deployment & Go-Live | Launch | 2027-01-15 | Alex Morgan | Not Started | 0% | 66
Formulas:
Settings = IF([Dashboard]="","",INDEX(tblTasks[End Date],MATCH([Dashboard],tblTasks[Task ID],0)))
Milestones = IF([Project Timeline]="","",INDEX(tblTasks[End Date],MATCH(SMALL(Settings!$U9:U49,1),Settings!$U9:U49,0)))

## Project Timeline
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
PROJECT TIMELINE & GANTT ROADMAP
Dynamic weekly calendar grid. Timeline bars, status highlights, and milestone indicators update automatically from task dates.
[13 empty] | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Task ID | Phase | Task Name | Owner | Start Date | End Date | Duration | Status | Priority | Comp % | Dep | Milestone | Schedule Alert | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15
TSK-01 | Discovery | Stakeholder Requirements Gathering | Alex Morgan | 2026-10-05 | 2026-10-12 | 8 | Completed | High | 100% | - | No | Completed | bar: 2026-10-05 to 2026-10-12
TSK-02 | Discovery | User Persona & Journey Mapping | Sarah Chen | 2026-10-08 | 2026-10-16 | 9 | Completed | Medium | 100% | TSK-01 | No | Completed | bar: 2026-10-05 to 2026-10-12
TSK-03 | Discovery | Discovery Phase Approval Sign-off | Alex Morgan | 2026-10-16 | 2026-10-16 | 1 | Completed | Critical | 100% | TSK-02 | Yes | Completed | bar: 2026-10-12
TSK-04 | Planning | System Architecture & Security Spec | Marcus Vance | 2026-10-19 | 2026-10-28 | 10 | Completed | High | 100% | TSK-03 | No | Completed | bar: 2026-10-19 to 2026-10-26
TSK-05 | Planning | Content Taxonomy & Helpdesk Schema | Elena Rostova | 2026-10-21 | 2026-11-04 | 15 | In Progress | High | 80% | TSK-04 | No | Overdue | bar: 2026-10-19 to 2026-11-02
TSK-06 | Planning | Project Roadmap & Resource Allocation | Alex Morgan | 2026-10-26 | 2026-11-04 | 10 | Completed | High | 100% | TSK-04 | Yes | Completed | bar: 2026-10-26 to 2026-11-02
TSK-07 | Design | Wireframe & UX Prototype Drafting | Sarah Chen | 2026-11-02 | 2026-11-16 | 15 | In Progress | Medium | 60% | TSK-06 | No | Due Soon | bar: 2026-11-02 to 2026-11-16
TSK-08 | Design | Brand Design System & UI Kit | Sarah Chen | 2026-11-09 | 2026-11-20 | 12 | In Progress | Medium | 25% | TSK-07 | No | In Progress | bar: 2026-11-09 to 2026-11-16
TSK-09 | Design | Client Prototype Review & Approval | Alex Morgan | 2026-11-20 | 2026-11-20 | 1 | Not Started | Critical | 0% | TSK-08 | Yes | Not Started | bar: 2026-11-16
TSK-10 | Build | Authentication & SSO Integration | Marcus Vance | 2026-11-23 | 2026-12-08 | 16 | Not Started | High | 0% | TSK-09 | No | Not Started | bar: 2026-11-23 to 2026-12-07
TSK-11 | Build | Customer Account & Profile Module | David Kim | 2026-11-25 | 2026-12-14 | 20 | Not Started | High | 0% | TSK-09 | No | Not Started | bar: 2026-11-23 to 2026-12-14
TSK-12 | Build | Billing & Payment Gateway API | David Kim | 2026-12-01 | 2026-12-18 | 18 | Blocked | Critical | 15% | TSK-10 | No | Blocked | bar: 2026-11-30 to 2026-12-14
TSK-13 | Build | Core Feature Integration Complete | Marcus Vance | 2026-12-18 | 2026-12-18 | 1 | Not Started | Critical | 0% | TSK-11 | Yes | Not Started | bar: 2026-12-14
TSK-14 | Testing | End-to-End Functional Test Suite | Elena Rostova | 2026-12-21 | 2027-01-04 | 15 | Not Started | High | 0% | TSK-13 | No | Not Started | bar: 2026-12-21 to 2027-01-04
TSK-15 | Testing | Security Audit & Vulnerability Assessment | Marcus Vance | 2026-12-28 | 2027-01-06 | 10 | Not Started | Critical | 0% | TSK-14 | No | Not Started | bar: 2026-12-28 to 2027-01-04
TSK-16 | Testing | UAT & Beta User Sign-Off | Alex Morgan | 2027-01-06 | 2027-01-06 | 1 | Not Started | Critical | 0% | TSK-15 | Yes | Not Started | bar: 2027-01-04
TSK-17 | Launch | Customer Support & Staff Training | Sarah Chen | 2027-01-07 | 2027-01-13 | 7 | Not Started | Medium | 0% | TSK-16 | No | Not Started | bar: 2027-01-04 to 2027-01-11
TSK-18 | Launch | Production Deployment & Go-Live | Alex Morgan | 2027-01-15 | 2027-01-15 | 1 | Not Started | Critical | 0% | TSK-17 | Yes | Not Started | bar: 2027-01-11
Formulas:
Settings = IF('Task List'!$[Dashboard]="","",'Task List'!G10)
Read Me = IF('Task List'!$[Dashboard]="","",'Task List'!H10)

## Task List
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
MASTER PROJECT TASK LIST
Main operational database (tblTasks). Enter tasks, dates, owners, and progress. Formulas calculate duration, overdue alerts, and days remaining.
Task ID | Phase | Task Name | Description | Owner | Start Date | End Date | Duration | Status | Priority | Completion % | Dependency Task ID | Milestone | Actual Completion Date | Days Remaining | Schedule Status | Notes
TSK-01 | Discovery | Stakeholder Requirements Gathering | Interview department heads and synthesize portal feature specifications. | Alex Morgan | 2026-10-05 | 2026-10-12 | 8 | Completed | High | 100% | - | No | 2026-10-12 | 0 | Completed | Approved by client committee.
TSK-02 | Discovery | User Persona & Journey Mapping | Define primary user workflows, permission tiers, and access levels. | Sarah Chen | 2026-10-08 | 2026-10-16 | 9 | Completed | Medium | 100% | TSK-01 | No | 2026-10-16 | 0 | Completed | 4 core persona flows established.
TSK-03 | Discovery | Discovery Phase Approval Sign-off | Executive governance gate sign-off on discovery deliverables and scope. | Alex Morgan | 2026-10-16 | 2026-10-16 | 1 | Completed | Critical | 100% | TSK-02 | Yes | 2026-10-16 | 0 | Completed | Formal sign-off milestone achieved.
TSK-04 | Planning | System Architecture & Security Spec | Define cloud infrastructure, database schema, and OAuth2 security guidelines. | Marcus Vance | 2026-10-19 | 2026-10-28 | 10 | Completed | High | 100% | TSK-03 | No | 2026-10-28 | 0 | Completed | SOC2 security baseline adopted.
TSK-05 | Planning | Content Taxonomy & Helpdesk Schema | Structure knowledge base categories, help documentation, and FAQs. | Elena Rostova | 2026-10-21 | 2026-11-04 | 15 | In Progress | High | 80% | TSK-04 | No |  | -6 | Overdue | Delayed review by legal; overdue relative to reporting date.
TSK-06 | Planning | Project Roadmap & Resource Allocation | Finalize sprint schedule, milestones, and contractor capacity plans. | Alex Morgan | 2026-10-26 | 2026-11-04 | 10 | Completed | High | 100% | TSK-04 | Yes | 2026-11-04 | 0 | Completed | Sprint timelines baselined.
TSK-07 | Design | Wireframe & UX Prototype Drafting | Design low-fidelity wireframes for customer dashboard and navigation. | Sarah Chen | 2026-11-02 | 2026-11-16 | 15 | In Progress | Medium | 60% | TSK-06 | No |  | 6 | Due Soon | Due in 6 days; active design reviews underway.
TSK-08 | Design | Brand Design System & UI Kit | Produce component library in Figma (buttons, tables, inputs, modals). | Sarah Chen | 2026-11-09 | 2026-11-20 | 12 | In Progress | Medium | 25% | TSK-07 | No |  | 10 | In Progress | Figma component tokens aligned to brand palette.
TSK-09 | Design | Client Prototype Review & Approval | Interactive prototype walkthrough with executive stakeholders. | Alex Morgan | 2026-11-20 | 2026-11-20 | 1 | Not Started | Critical | 0% | TSK-08 | Yes |  | 10 | Not Started | Design freeze milestone gate.
TSK-10 | Build | Authentication & SSO Integration | Implement Google Workspace and Microsoft Azure AD single sign-on. | Marcus Vance | 2026-11-23 | 2026-12-08 | 16 | Not Started | High | 0% | TSK-09 | No |  | 28 | Not Started | Prerequisite for all profile and billing modules.
TSK-11 | Build | Customer Account & Profile Module | Build self-service settings, profile editing, and password reset flows. | David Kim | 2026-11-25 | 2026-12-14 | 20 | Not Started | High | 0% | TSK-09 | No |  | 34 | Not Started | REST API backend endpoints defined.
TSK-12 | Build | Billing & Payment Gateway API | Integrate Stripe recurring billing, invoice download, and webhooks. | David Kim | 2026-12-01 | 2026-12-18 | 18 | Blocked | Critical | 15% | TSK-10 | No |  | 38 | Blocked | BLOCKED: Awaiting corporate merchant account verification.
TSK-13 | Build | Core Feature Integration Complete | Assemble all modules into unified staging environment build. | Marcus Vance | 2026-12-18 | 2026-12-18 | 1 | Not Started | Critical | 0% | TSK-11 | Yes |  | 38 | Not Started | Alpha build gate sign-off.
TSK-14 | Testing | End-to-End Functional Test Suite | Execute automated regression tests, edge cases, and browser compatibility. | Elena Rostova | 2026-12-21 | 2027-01-04 | 15 | Not Started | High | 0% | TSK-13 | No |  | 55 | Not Started | Target 95%+ automated test pass rate.
TSK-15 | Testing | Security Audit & Vulnerability Assessment | Third-party penetration testing and OWASP compliance review. | Marcus Vance | 2026-12-28 | 2027-01-06 | 10 | Not Started | Critical | 0% | TSK-14 | No |  | 57 | Not Started | Zero high-severity vulnerabilities required.
TSK-16 | Testing | UAT & Beta User Sign-Off | Pilot test with 25 key customer representatives and synthesize feedback. | Alex Morgan | 2027-01-06 | 2027-01-06 | 1 | Not Started | Critical | 0% | TSK-15 | Yes |  | 57 | Not Started | Beta acceptance threshold: 90%+ satisfaction.
TSK-17 | Launch | Customer Support & Staff Training | Conduct training sessions for customer success and support staff. | Sarah Chen | 2027-01-07 | 2027-01-13 | 7 | Not Started | Medium | 0% | TSK-16 | No |  | 64 | Not Started | Training video library & helpdocs published.
TSK-18 | Launch | Production Deployment & Go-Live | Cutover DNS, execute production migration, and announce live portal. | Alex Morgan | 2027-01-15 | 2027-01-15 | 1 | Not Started | Critical | 0% | TSK-17 | Yes |  | 66 | Not Started | Official public launch milestone.

## Milestones
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
PROJECT MILESTONES REGISTER
Governance gates, stage sign-offs, and critical delivery checkpoints. Directly synchronized with project task tracking.
TOTAL MILESTONES |  | COMPLETED GATES |  | UPCOMING / PENDING |  | MILESTONE DELIVERIES
6 |  | 2 |  | 4 |  | 33.33%
Milestone ID | Milestone Name | Phase | Owner | Target Date | Status | Completion % | Days Remaining | Sign-Off Criteria / Notes
M-01 | Discovery Phase Approval Sign-off | Discovery | Alex Morgan | 2026-10-16 | Completed | 100% | 0 | Formal sign-off milestone achieved.
M-02 | Project Roadmap & Resource Allocation | Planning | Alex Morgan | 2026-11-04 | Completed | 100% | 0 | Sprint timelines baselined.
M-03 | Client Prototype Review & Approval | Design | Alex Morgan | 2026-11-20 | Not Started | 0% | 10 | Design freeze milestone gate.
M-04 | Core Feature Integration Complete | Build | Marcus Vance | 2026-12-18 | Not Started | 0% | 38 | Alpha build gate sign-off.
M-05 | UAT & Beta User Sign-Off | Testing | Alex Morgan | 2027-01-06 | Not Started | 0% | 57 | Beta acceptance threshold: 90%+ satisfaction.
M-06 | Production Deployment & Go-Live | Launch | Alex Morgan | 2027-01-15 | Not Started | 0% | 66 | Official public launch milestone.
Formulas:
Settings = IF([Project Timeline]="","",INDEX(tblTasks[End Date],MATCH(SMALL(Settings!$V9:V49,1),Settings!$V9:V49,0)))

## Settings
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
PROJECT PARAMETERS
Project Name |  | Customer Portal Launch
Project Manager |  | Alex Morgan, PMP
Project Start Date |  | 2026-10-05 |  | MASTER LOOKUP LISTS (DATA VALIDATION) | [5 empty] | DASHBOARD CHART AGGREGATIONS (AUTOMATED)
Target End Date |  | 2027-01-15 |  | Project Phase | Team Member | Task Status | Priority Level | Milestone Flag | Schedule Status Definition
Reporting Date (Ref) |  | 2026-11-10 |  | Discovery | Alex Morgan | Not Started | Low | Yes | Completed |  |  |  |  | 1e+99 | 1e+99 | 1e+99
Overall Project Health |  | At Risk |  | Planning | Sarah Chen | In Progress | Medium | No | In Progress |  |  |  |  | 1e+99 | 1e+99 | 1e+99
|  |  |  | Design | Marcus Vance | Blocked | High |  | Due Soon (<=7d) |  |  |  |  | 1e+99 | 1e+99 | 46311
NOTE ON REPORTING DATE: Cell D9 determines the baseline for 'Days Remaining', 'Due Soon', and 'Overdue' calculations. For live daily tracking, enter =TODAY(). For historical reviews or testing, enter a fixed calendar date. |  |  |  | Build | Elena Rostova | Completed | Critical |  | Overdue (<0d) |  |  |  |  | 1e+99 | 1e+99 | 1e+99
|  |  |  | Testing | David Kim | On Hold |  |  | Blocked |  |  |  |  | 5 | 1e+99 | 1e+99
|  |  |  | Launch |  |  |  |  | Not Started | Status | Count |  |  | 1e+99 | 1e+99 | 46330.0001
[9 empty] | On Hold | Completed | 5 |  |  | 1e+99 | 1e+99 | 1e+99
[9 empty] | Check Dates | In Progress | 3 |  |  | 1e+99 | 1e+99 | 1e+99
[9 empty] | Check Completion | Not Started | 9 |  |  | 1e+99 | 46346.0001 | 46346.0001
[10 empty] | Blocked | 1 |  |  | 1e+99 | 1e+99 | 1e+99
[10 empty] | On Hold | 0 |  |  | 1e+99 | 1e+99 | 1e+99
[14 empty] | 12 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 46374.0001 | 46374.0001
[14 empty] | 1e+99 | 1e+99 | 1e+99
[10 empty] | Project Phase | Total Tasks | Completed | Phase Progress % | 1e+99 | 1e+99 | 1e+99
[10 empty] | Discovery | 3 | 3 | 100% | 1e+99 | 46393.0002 | 46393.0002
[10 empty] | Planning | 3 | 2 | 93.33% | 1e+99 | 1e+99 | 1e+99
[10 empty] | Design | 3 | 0 | 28.33% | 1e+99 | 46402.0002 | 46402.0002
[10 empty] | Build | 4 | 0 | 3.75% | 1e+99 | 1e+99 | 1e+99
[10 empty] | Testing | 3 | 0 | 0% | 1e+99 | 1e+99 | 1e+99
[10 empty] | Launch | 2 | 0 | 0% | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99
[14 empty] | 1e+99 | 1e+99 | 1e+99

## Read Me
SIMPLE OFFICE AI ¦ Project Timeline & Lightweight Gantt Planner
Dashboard | Project Timeline | Task List | Milestones | Settings | Read Me
SIMPLE OFFICE AI — PROJECT TIMELINE & GANTT TEMPLATE USER GUIDE
Operating instructions, calculation methodology, table auto-expansion rules, and best practices.
1. EXECUTIVE OVERVIEW & WORKBOOK PURPOSE
The Simple Office AI Project Timeline Template is a lightweight, macro-free project management workbook built for Excel 365. It gives small businesses, freelancers, operations leads, and project managers a practical Gantt-style planning system with a SaaS/ERP visual structure. Key capabilities: • 20-week Gantt view with weekly date columns and status-colored timeline bars. • Master task database (tblTasks) with 41 prepared task rows, dropdowns, date validation, and schedule warnings. • Formula-driven KPIs, charts, top action items, upcoming milestones, and project health. • Dynamic milestone register supporting up to 15 milestones. • Zero VBA, zero macros, zero paid plugins, and zero external connections.
2. WORKBOOK ARCHITECTURE & SHEET SUMMARY
The workbook contains 6 worksheets in workflow order: 1. Dashboard: 8 KPIs, 3 charts, the top two overdue/blocked tasks, the next four milestones, and project health. 2. Project Timeline: 20-week Gantt view for up to 41 prepared task rows. 3. Task List: Main editable Excel table (tblTasks). 4. Milestones: Date-sorted register for up to 15 milestone tasks. 5. Settings: Project parameters, validation lists, and chart calculations. 6. Read Me: Usage instructions, rules, capacity, and limitations.
3. HOW TO REPLACE SAMPLE DATA & ADD NEW TASKS
To adapt this workbook: Step 1: In Settings, update Project Name, Manager, Start Date, Target End Date, and Reporting Date. Step 2: Update team members and phases in the lookup lists. Step 3: Replace the sample task rows in Task List. Step 4: Use the prepared rows through row 50. Formulas, validation, warnings, Dashboard metrics, Milestones, and Timeline links are already configured for these 41 task rows. Step 5: Use YYYY-MM-DD dates. End Date cannot be earlier than Start Date. Step 6: If more than 41 tasks, more than 15 milestones, or more than 20 timeline weeks are needed, extend the prepared ranges before entering additional records.
4. SCHEDULE STATUS & OVERDUE DETECTION LOGIC
Schedule Status uses this formula order: • Check Dates: End Date is earlier than Start Date. • Check Completion: Status is Completed but Completion % is not 100% or Actual Completion Date is blank. • Completed: Completed with 100% and an Actual Completion Date. • Blocked / On Hold: Reflects the selected Status. • Overdue: End Date is earlier than Reporting Date and the task is incomplete. • Due Soon: End Date falls within 7 calendar days of Reporting Date. • In Progress / Not Started: Remaining operating states. Duplicate Task IDs are highlighted because IDs are used for dependencies and lookups.
5. PROJECT HEALTH FORMULA & GOVERNANCE MATRIX
Project Health is formula-driven: • Not Started: No task IDs entered. • On Track: No blocked or overdue tasks, and completion is not more than 10 percentage points behind elapsed schedule. • At Risk: At least one blocked/overdue task, or completion is 10–20 percentage points behind elapsed schedule. • Off Track: At least 2 blocked tasks, at least 3 overdue tasks, or completion is more than 20 percentage points behind elapsed schedule. Elapsed schedule is bounded between 0% and 100% using Project Start, Target End, and Reporting Date. Formula: Settings!D10; Dashboard display: M6.
6. COLOR CONVENTIONS & DESIGN SYSTEM
The template utilizes a standardized SaaS design palette: • Deep Navy (#0F2747): Header banners, table headers, milestone markers. • Primary Blue (#2563EB): Active navigation tabs, primary planned timeline bars, progress percentages. • Emerald Green (#10B981): Completed tasks, 100% completion flags, 'On Track' health badge. • Amber Orange (#F59E0B): 'Due Soon' warnings, 'At Risk' status, high-priority flags. • Ruby Red (#DC2626): Overdue tasks, critical blockers, 'Off Track' status alerts. • Soft Blue Cell Fill (#EFF6FF): Signals editable user input cells. • White / Light Gray Fill: Calculated automated cells (do not overwrite formulas).
7. EXCEL 365 COMPATIBILITY & TECHNICAL SPECIFICATIONS
• Optimized for Microsoft Excel 365 and Excel 2021+. • Macro-free and built with standard workbook formulas, tables, validation, charts, and conditional formatting. • Prepared capacity: 41 tasks, 15 milestones, and a 20-week Gantt horizon. • Google Sheets compatibility is not claimed until native conversion and testing are completed. • The template supports operational planning; it does not replace enterprise project-management software with resource leveling and advanced dependency scheduling. • Data safety: avoid entering passwords, payment-card data, government IDs, or other sensitive personal information into a shared copy.