## Sheet1
FQHC Readiness Timeline Table
Not Started
Use this table to outline key milestones and readiness checkpoints when preparing for FQHC designation and operational readiness. | [5 empty] | In Progress
Complete
Phase | Timeline | Key Activities | Responsible Party | Readiness Status | Notes
Planning | Months 0-3 | Needs assessment, board alignment | CEO/CFO | Complete | Initial approval secured
Application | Months 3-6 | HRSA application prep | CFO/Admin | In Progress | Financial projections underway
Pre-Operational | Months 6-9 | Policy development, staffing | Leadership | Not Started | Requires finalized policies and staffed positions prior to go live.
Financial Leadership for Community Health Center CFOs
Tool Version: v1.0 ¦ Updated: January 2026 ¦ © Cris Julian