## Instructions
Purpose
The purpose of a RASCI chart is to ensure every stakeholder in a project is aware of their role and responsibility.
| R | Responsible | Who does the work
| A | Accountable | The one who owns the outcome
| S | Supports | Who is assisting the responsible
| C | Consulted | Who is assisting the responsible with input, not work
| I | Informed | Those who need updates, information, etc.
Of all of these, if you have a small team, I find that Support can often be dropped from the list due to redundancy. Some just use the R and A so choose what makes sense for you. To update the options, go to Data Validation, then list and delete the ones you don't want to use.
Instructions
1 | Enter your project name and milestones
2 | Enter your roles across the top
3 | Determine your priorities and statuses. To update, go to Data Validation, then list and edit.
4 | To edit colors, select the cells and go to Conditional Formatting then manage rules. You may adjust colors here.
5 | To edit the chart colors, double click on the chart and change fill off to the right. If you can't select cells near a chart, click off to the side and navigate with arrow keys, the chart is blocking them
6 | There are no 'rules' to the counts for the letters but there are guidelines
A needs to have 1 per milestone, too many is confusing and you must have one
R should have 1 to 3, too many makes it unclear who is doing work
C is a 2-way communication role so the more you have the slower decision making becomes
I is one-way communication, use as many as needed but try to keep them in proportion and not have a whole chart full of I
S this is the least used, many milestones will have zero
7 | Row 28 to 32 are hidden, you can right click and unhide, they are set up if you need more rows but you can keep adding, just adjust conditional formatting to capture as noted above. If you right click in the middle of the chart and insert rows, you won't have to worry about adjusting formulas
8 | Starting in row 38m, the counts are there for the charts at the top, the text is white. If you need more rows and type over what is there, you will lose those so drag them somewhere else.
9 | If you need fewer columns, you can righ click and hide making sure there are no values in the cells. You will need to adjust chart size by clicking on the circles in the corners and dragging them
If you need custom work, contact me, nicole.hullihen@hotmail.com
Click to open Google Sheets

## RASCI
| Project Name | R | Responsible | 1
|  | A | Accountable | 1
|  | S | Supports | 1
|  | C | Consulted | 1
|  | I | Informed | 1
| Milestone | Priority | Status | Date | Executive Leadership | Project Mgmt | Product Mgmt | Business Analysis | UI/UX Design | Dev/Engineering | QA/Testing | DevOps/Infra | Security/Compliance | Data/Analytics | Customer Success/Support | Sales/Marketing | Training/Enablement
| Project Kickoff & Team Alignment | High | In Progress | 2025-08-15 | R | A | S | C | I
| Requirements Gathering Completed | Med | Done | 2025-08-17
| Requirements Sign-Off | Low | Needs Review | 2025-08-17
| Initial Project Plan & Timeline Approved |  | On Hold | 2025-08-19
| System Architecture Defined |  | Not Started | 2025-08-25
| UI/UX Design Completed |  |  | 2025-08-30
| Design Sign-Off |  |  | 2025-08-30
| Development Environment Setup |  |  | 2025-09-03
| Core Framework/Infrastructure Built |  |  | 2025-09-08
| First Feature Developed & Tested |  |  | 2025-09-11
| Midpoint Development Review |  |  | 2025-09-15
| Integration of Key Features Completed |  |  | 2025-09-22
| System Testing Completed |  |  | 2025-09-23
| UAT (User Acceptance Testing) Started |  |  | 2025-09-25
| UAT Sign-Off |  |  | 2025-09-28
| Security & Compliance Review Passed |  |  | 2025-09-30
| Performance Testing Completed |  |  | 2025-10-02
| Go/No-Go Decision |  |  | 2025-10-04
| Product Launch / Deployment |  |  | 2025-10-06
| Post-Launch Review & Handove |  |  | 2025-10-08
High | 1 | In Progress | 1
Med | 1 | Not Started | 1
Low | 1 | Done | 1
|  | On Hold | 1
|  | Needs Review | 1